REPUBLIC OF SLOVENIA

INTERGOVERNMENTAL CONFERENCE ON THE ACCESSION OF

THE REPUBLIC OF SLOVENIA TO THE EUROPEAN UNION

ADDITIONAL CLARIFICATIONS TO THE NEGOTIATING POSITION

ON CHAPTER 24 –

JUSTICE AND HOME AFFAIRS

In its additional clarifications CONF-SI 15/01, the Republic of Slovenia stated that its more detailed measures and plan to establish control of the future external border of the European Union would be presented in the Schengen Action Plan. The Republic of Slovenia wishes to inform the Accession Conference that the Government of the Republic of Slovenia on its session held on 24 May 2001 adopted the Action plan for the implementation of Schengen standards to control the future external border of the European Union (Annex 1).

Ljubljana, 28 May 2001

Annex 1

REPUBLIC OF SLOVENIA

ACTION PLAN FOR THE IMPLEMENTATION OF SCHENGEN STANDARDS TO CONTROL THE FUTURE EXTERNAL BORDER OF THE EUROPEAN UNION

Ljubljana, May 2001

ACTION PLAN FOR THE IMPLEMENTATION OF SCHENGEN STANDARDS TO CONTROL THE FUTURE BORDER OF THE EUROPEAN UNION

CONTENTS:

# INTRODUCTORY EXPLANATIONS

# GEOGRAPHICAL CHARACTERISTICS, TYPES AND NUMBER OF BORDER CROSSING POINTS WITHIN THE TERRITORY OF THE REPUBLIC OF SLOVENIA AND ON THE FUTURE EXTERNAL BORDER OF THE EUROPEAN UNION

Annex: map showing border crossing points

# STATE BORDER CONTROL – COMPETENCES OF THE MINISTRY OF THE INTERIOR (THE POLICE), ORGANISATION, ALIGNMENT WITH THE ACQUIS

## State border control  – organisation

Annexes:

- organisational chart of the Ministry of the Interior

- organisational chart of the Police

3.2    Alignment with the acquis and planned measures

3.3    Organisation and personnel structure for the implementation of state border control

3.4    Education and training

Annex: action plan for professional training programmes

3.5 Information/telecommunications system and the setting up and operation of the Schengen Information System

3.5.1 Setting up of the Schengen Information System (SIS) and its operation

3.5.2 Setting up of a technical assistance unit (SIRENE)

3.5.3 Application of the Schengen Information System (SIS)

Annex: action plan for the realisation of projects

3.6    Technical equipment for the control of the future external border

3.7    Specific measures at airports and sea ports

3.8    Measures on internal borders and within the country; police cooperation

4.   HARMONISATION OF THE VISA POLICY OF THE REPUBLIC OF SLOVENIA WITH SCHENGEN STANDARDS

4.1    Harmonisation with the acquis

4.2    Education and training

4.3    Visa information system

4.4    Security standards for consular (visa) work

Annexes:

- visa sample

- visa application

- residence permit sample

- visa information system and links

- action plan for the setting up of the visa information system

# 5. IMPLEMENTATION OF SCHENGEN AGREEMENT PROVISIONS ON DATA   PROTECTION

6. TECHNICAL ASSISTANCE OF THE EUROPEAN UNION AND FINANCIAL REALISATION PROGRAMME FOR THE SETTING UP OF CONTROL ON THE FUTURE EXTERNAL BORDER OF THE EUROPEAN UNION

6.1  Technical assistance of the European Union in implementing the strategy contained in the chapter 'Justice and Home Affairs'

6.2  Financial realisation plan for the project of setting up the state border control on the future external border of the European Union

7.   INFRASTRUCTURE PROGRAMME FOR THE FUTURE EXTERNAL BORDER OF THE EUROPEAN UNION

7.1  Activities of the Government of the Republic of Slovenia for the setting up of the external border of the European Union (infrastructure)

7.2  Activities of bodies responsible for the setting up of security and customs controls and inspection control

7.3 Plan for the setting up of 'Border inspection posts' (BIP) and the construction or renovation of border crossing points on the state border with the Republic of Croatia (and the control of the future external border)

ACTION PLAN FOR THE IMPLEMENTATION OF SCHENGEN STANDARDS TO CONTROL THE FUTURE BORDER OF THE EUROPEAN UNION

# 1. INTRODUCTORY EXPLANATION

The legislation of the Republic of Slovenia in the field of "justice and home affairs" has been already to a great extent aligned with the acquis and Schengen ACQUIS. This evaluation was written in negotiating positions and further enforced in additional clarifications to the negotiating position of the Republic of Slovenia in the area of "justice and home affairs " presented to the EU Commission last year. In this context it was stressed that the Republic of Slovenia did not request any transitional periods or derogations and that the legislation in the area of “justice and home affairs” would be fully aligned with the acquis by the end of 2002 at latest. This opinion and evaluation was not changed in further additional clarifications to the negotiating positions in this field which the Government of the Republic of Slovenia discussed and adopted at the meeting held on 19 April 2001.

The last two years saw the adoption of the majority of legislation foreseen in the national programme both in the area of migration and in the area of combat against organised crime and other areas important for the full implementation of the Schengen acquis. The level of alignment with the acquis was described in the negotiating positions and both supplements. A detailed description of the level of alignment with the Schengen acquis and individual documents are presented in the harmonogramme in annex.

Adopted in the area of migration were all planned acts regulating the area of asylum, aliens' problems, aliens' employment and visa regime, namely: Resolution on Immigration Policy of the Republic of Slovenia, Aliens Act, Asylum Act, Act on Prevention of Illegal Work and Employment and Act on Employment and Work of Aliens. Last year saw the adoption of the planned secondary legislation from the area of alien problems and asylum providing detailed definitions of individual procedures, the way of alien treatment and forms of protection the Republic of Slovenia offers to different categories of refugees.

Visa policy, which is fully aligned with the EU standards, was fully implemented too. Great attention was paid also to the preparation of new documents from passports to alien documents. Previous year saw the adoption of the Travel Documents of Citizens of the Republic of Slovenia Act. New visa stickers and residence permits are valid too.

In the area of crime and criminal law legislation was adopted rounding up the modernisation of criminal law system. Thus the legislation of the Republic of Slovenia already contains largely aligned provisions of the acquis referring to an efficient combat of organised crime especially in the area of combat against corruption, protection of financial interests of the EU and the Member States, combat against terrorism and other forms. Also adopted is all planned legislation from the area of drugs, namely: Act on the manufacture and trafficking of illicit drugs, Act on the prevention of the use of illicit drugs and treatment of illicit drugs users, and Act on the precursors for illicit drugs.

In the framework of police and judicial cooperation in criminal matters a step forward was taken towards the final alignment with the acquis. With a number of already adopted international conventions, we signed and ratified individual international conventions from the area of corruption, prevention of illicit drug trade, prevention of transnational crime and other, simultaneously fulfilling obligations from the National Programme for the adoption of the acquis. In line with the National Programme Slovenia foresees to adopt by the end of 2002 all international agreements from the area of judicial cooperation in criminal matters which Slovenia can ratify before the EU accession and which are a component of the acquis in this area.

In the framework of bilateral cooperation in the area of police cooperation, combat of crime and other forms of crime, the Republic of Slovenia signed agreements with 16 countries. In the area of readmission of persons who illegally entered or reside in the area of one of the countries, the agreement was signed with 22 countries. Only in the last six months Slovenia concluded the agreements with Germany on the cooperation in combat against serious criminal offences, with the Kingdom of Belgium on police cooperation, with Russian Federation on the cooperation in combat against organised crime, with Federal Republic of Yugoslavia on the combat against organised crime, terrorism and other forms of serious criminal offences and the agreement on readmission of persons who illegally entered or reside in the area of one of the countries; a similar agreement was concluded with Romania too. It closed negotiations with Bulgaria and Greece, while negotiations on the conclusion of similar agreements with Bosnia and Herzegovina, Iran, Turkey, UK, France, Estonia, Lithuania and Latvia are underway.

Also in other areas included in the acquis Slovenia adopted rules enforcing requirements defined in the convention, especially Weapons Act, Transport of Hazardous Substances Act with secondary legislation providing a detailed definition of the supervision of vehicles transporting hazardous substances, and other. An important progress was made also in the forming of the common Schengen information system. Personal Data Protection Act enforces the provisions of the EU Directives and Schengen Agreement, which largely perform all requirements of the named documents.

A comparative analysis of the adoption of the Schengen acquis and its implementation in the legislation of the Republic of Slovenia reveals that most provisions concerning state border control, state border crossing, visa regime, residence documents, asylum provisions, legal aid in criminal matters, area of drugs, firearms and data protection are already enforced. In line with the National programme for the adoption of the acquis by the end of 2002 it is foreseen that the legislation will be fully enforced to the extent possible before the full membership of Slovenia in the EU.

Enforcement of the Schengen Agreement provisions and established control of the future EU external border represent one of the most comprehensive and financially most demanding projects from the area of migration. In this context Slovenia relied on the technical assistance of the European Union provided through the Phare programme, both in the area of institution building and in the area of investment. In terms of contents, Slovenia planned, completed or is still implementing three (3) »twinning« projects solely in the area of migration:

- two »twinning« projects in the area of state border control, first finished in 2000, the second will be finished in 2001. With the assistance of partner countries (Germany, Austria), Slovenia defined in the framework of the first programme necessary preconditions to establish state border control, technical standards of state border protection, border crossings, »green« and »blue« borders, airports, ports, for technical equipment necessary for information system establishment, staff structure and programmes of expert education required for meeting these standards. In the framework of the second programme the stress lies on the programmes of expert education, training of trainers and preparation of regulations for the full alignment of legislation with the requirements of the Schengen acquis;

- 2000 saw the completion also of the "twinning" project whose aim was to further align Slovenian legislation in the area of migration and alien policy with a special stress on visa policy and practice (partner country Austria);

- the integrate programme of institution building includes also »twinning« projects from the area of "prevention of organised crime" and "police cooperation", which will begin to be implemented in 2001 and 2002 respectively.

Recommendations of both already finished projects represent important guidelines for the preparation of changes and amendments to Aliens Act and Asylum Act, and, in the framework of further implementation of the project, also for the preparation of the new State Border Control Act and other provisions and international agreements. The planned measures and individual projects for the implementation of all technical standards for the implementation of efficient state border control and Schengen Information System were also prepared in cooperation with partner countries, EU Member States, and represent an important support in the preparation of »Schengen Action Plan«. In 1999, the Minister of the Interior adopted the decision on the appointment of project and sub-project working groups for the preparation of implementation plans for the implementation of the Schengen acquis.

In terms of contents and methodology the »Schengen Action Plan« represents an implementation, operative programme of measures which the Republic of Slovenia has to implement to fully enforce the Schengen acquis and technical standards for the supervision of the future external border of the EU. The framework of the action plan therefore focuses on the presentation or analysis of the present state in the adoption of the Schengen acquis in the area of data protection, aliens' problems, visa policy and state border control. It defines the planned changes or amendments to legal acts and the preparation of new, the essential part of the plan being foreseen measures for the establishment of efficient state border control such as: provision of necessary staff structure, programmes of expert education, plan of necessary technical equipment to establish the Schengen Information System, and control of border crossings and state border.

The implementation of all these projects is relatively dependent also on necessary financial resources and technical assistance of the EU. Therefore the plan includes also the structure of necessary funding for the implementation of the integrate action plan.

# GEOGRAPHICAL CHARACTERISTICS, TYPES AND NUMBER OF BORDER CROSSING POINTS WITHIN THE TERRITORY OF THE REPUBLIC OF SLOVENIA AND ON THE FUTURE EXTERNAL BORDER OF THE EUROPEAN UNION

(Annex 1.1)

The total length of Slovenia's state border is 1382 km. There are 163 border crossing points of various categories along this border. Border crossing points are divided by location and type into road, railway, airport and sea/river borders, and by structure of traffic into border crossing points for international traffic (64), border crossing points for interstate traffic (17) border crossing points for border region traffic (41), and border crossing points according to special bilateral agreements (a total of 41: 20 agricultural crossing points and 21 mountain crossing points). State borders and border crossing points are shown in the annex. The Republic of Slovenia borders four states:

- in the north the Republic of Slovenia borders the Republic of Austria (an external border of the European Union). The total length of the land and river border with the Republic of Austria is 330 kilometres. There are 55 border crossing points of various categories along this border;

- in the west the Republic of Slovenia borders the Republic of Italy, another Member State of the European Union. The land border with Italy is 232 kilometres long, and the sea border is 48 kilometres long. There are 60 border crossing points on the border with the Republic of Italy;

- in the south the Republic of Slovenia borders the Republic of Croatia. The border is not yet finally determined. According to figures from the Geodesy Institute of the Republic of Slovenia the land and river border with Croatia measures 670 kilometres long while the length of the sea border is not yet defined. There are 36 border crossing points on the border with the Republic of Croatia;

- in the east the Republic of Slovenia borders the Republic of Hungary. The land and river border with Hungary measures 102 kilometres. There are 6 border crossing points of various categories on this border.

In addition to the above there are three (3) border crossing points for international airport traffic. These are: Ljubljana Airport (at Brnik), Maribor Airport (at Slivnica) and Portorož Airport (at Sečovlje). There are also three (3) border crossing points for international maritime traffic. These are: Koper, Piran and Izola.

The future external border of the European Union is expected to run along the state border with the Republic of Croatia (the measures envisaged in the plan proceed from this assumption). From the administrative point of view 29 municipalities, with a total population of around 340,000 inhabitants, adjoin the Croatian state border. There are 39 border crossing points along this border, two of which are currently out of service. Some municipalities have several border crossing points (road, rail, airport or sea), while only eight border municipalities currently have no international or interstate border crossing. The table below gives details of the border municipalities including population, number of houses and border crossing points.

| Municipality | - Total number of houses | Total number of inhabitants | ## Border crossing posts (BCPs) |
| --- | --- | --- | --- |
| LENDAVA | 3928 | 12540 | Lendava - rail MP Petišovci |
| ČRENŠOVCI | 1318 | 4520 |  |
| RAZKRIŽJE | 435 | 1361 | Razkrižje; Gibina |
| ORMOŽ | 6026 | 17330 | Središče ob Dravi, Središče ob Dravi – rail MP Ormož |
| GORIŠNICA | 2440 | 6075 | ### Meje (out of service) |
| VIDEM | 2169 | 5617 | Zgornji Leskovec |
| ZAVRČ | 760 | 1460 | Zavrč |
| PODLEHNIK | 1000 | 1960 | Gruškovje |
| ŽETALE | 496 | 1417 |  |
| ROGAŠKA SLATINA | 2868 | 11366 |  |
| ROGATEC | 1103 | 3376 | Rogatec Rogatec – rail MP Dobovec |
| PODČETRTEK | 1264 | 3516 | Imeno Imeno – rail MP |
| BISTRICA OB SOTLI | 545 | 1593 | Bistrica ob Sotli |
| KRŠKO | 8034 | 29477 |  |
| BREŽICE | 8543 | 28734 | Orešje Dobova – rail MP Rigonce Obrežje Slovenska vas |
| NOVO MESTO | 10867 | 43254 |  |
| ŠENTJERNEJ | 2214 | 6647 |  |
| KOČEVJE | 3436 | 17692 |  |
| LOŠKA DOLINA | 1202 | 3562 | Babno polje |
| LOŠKI POTOK | 763 | 2186 | Podplanina |
| - METLIKA | 2512 | 8499 | Metlika Metlika – rail MP |
| ILIRSKA BISTRICA | 4501 | 16200 | Ilirska Bistrica – rail MP Jelšane Starod |
| HRPELJE-KOZINA | 1573 | 4366 |  |
| ČRNOMELJ | 4186 | 15583 | Vinica |
| KOPER | 11728 | 50495 | Luka Koper – sea MP Rakitovec – rail MP Sočerga Podgorje (out of service)) |
| OSILNICA | 197 | 456 |  |
| IZOLA | 2719 | 16081 | Izola – sea MP |
| PIRAN | 4271 | 19074 | Portorož – sea MP Dragonja Sečovlje |
| KOSTEL | 528 | 763 | Petrina |

# STATE BORDER CONTROL – COMPETENCES OF THE MINISTRY OF THE INTERIOR (THE POLICE), ORGANISATION, ALIGNMENT WITH THE ACQUIS

# 3.1 State border control  – organisation

(Annexes 1.2, 1.3, 1.4)

The competent authority for state border control (border controls and protection of the state border) is the police, which is a body within the structure of the Ministry of the Interior, while the competent authority for the control of goods is the Ministry of Finance, or rather with the Customs Administration. The Veterinary Administration and the inspection services of the Ministry of Agriculture, Forestry and Food also have certain powers at border crossing points over which specific types of goods are transported. At all international and interstate border crossing points checks are carried out by both police and customs officials, while at border crossing points for border region traffic to and from Austria and Italy only customs controls are carried out. The police and the customs service each have their own statutory powers but the Administration Act requires them to cooperate on joint matters (detection of the trafficking in arms, narcotics, etc.).

The police carry out controls at and along the state border, in the border area and in the interior of the country (checking documents permitting the crossing of the state border, checks on persons, checks on vehicles and checks on goods transported over the state border). As a rule these checks are performed at border crossing points but when the relevant legal conditions are fulfilled (Article 10 of the Border Control Act) they are also carried out at places on the state border between official crossing points. Border controls at major border crossing points and border crossing points that are important from the point of view of security are carried out by border police stations with a specialised area of operation. Controls at other border crossing points are carried out by border police stations with a combined area of operation and by other police stations with combined areas of operation in whose territory the border crossing point lies or through which the state border runs.

Border checks at border crossing points consist of basic border checks, thorough border checks and the reporting of refusal or entry into the country. Slovene citizens, persons with diplomatic or official passports and citizens of states not defined as security risks are as a rule subjected to basic border checks. Citizens of states which are a security risk are subjected to thorough border checks, as are aliens if there are grounds for suspicion that their travel documents are not genuine. Reporting of entry or of refusal of entry covers the issuing of a visa, stamping the travel document and data input on entry or refusal of entry into computer records.

The organisation of Slovenia's border police, like that of the Slovene police force as a whole, is based on three levels: local, regional and national (see the organisational chart of the Ministry and the police in annex)

At the local level control is effected at and along the state border and in the border region by 16 border police stations with a special area of operation (15 border police stations and 1 maritime police station), 9 border police stations with a combined area of operation (8 border police stations and 1 airport police station) and 31 police units with a combined area of operation (29 police stations and 2 police departments). The total number of police officers carrying out border control tasks at the 56 police units whose territory contains a border crossing point or part of the state border is around 1090.

There are a further 55 police units (45 police stations and 10 departments) in the Republic of Slovenia operating at the local level whose territory contains no border crossing point or section of the state border. These are staffed by around 3500 police officers. In addition to their general police duties they also take part in the surveillance of aliens inside the country.

At the regional level (11 police directorates) the work of controlling the state border is carried out by state border and aliens inspectors (20). Seven (7) police directorates have state border and aliens groups while in the other four (4) this work is carried out by inspectors in the offices of the uniformed force. Officers from criminal investigation offices also take part in border control work. The tasks of the state border and aliens groups and of the inspectors are as follows:

- monitoring, analysing, studying and assessing security conditions and the effectiveness and efficiency of police work and the use of powers in the protection of the state border, border checks, investigation of border incidents and procedures with aliens;

- monitoring, analysing, studying and assessing security conditions and the effectiveness and efficiency of police work in relation to security at airports;

- ensuring the performance of tasks from their own area of operation when coordinated operation in the area of a police directorate is required;

- ensuring the lawful implementation of regulations and the planning and implementation of measures for effective police work within their own area of operation;

- providing specialised assistance and effecting supervision of the work of police stations and proposing measures to improve security conditions;

- planning and harmonising the preventive activities of police stations;

- first-instance administrative proceedings in relation to crossing the state border and the construction and installation of facilities at border crossing points and along the state border;

- providing the public with appropriate information relating to their own area of operation and cooperation with the border region security bodies of neighbouring countries.

At the national level border control operations are undertaken by the State Border and Aliens Section of the Uniformed Police Directorate (an organisational unit of the General Police Directorate). The Section consists of a State Border Division and an Illegal Migrations and Aliens Division.

The Section's main tasks are planning, organising, technical orientation and supervision of the execution of tasks of police directorates; direct measures and the management of difficult operations relating to border issues and aliens in cases where the difficulty of the operations exceeds the personnel, professional or technical capacities of other organisational units of the police; cooperation in the preparation of regulations relating to the Sector's area of operations; and cooperation with foreign security bodies and international institutions.

Border control operations are also undertaken by the Aliens Centre and the Airport Police Unit of the Uniformed Police Directorate. Operations relating to the detection and prevention of cross-border crime are undertaken by the Criminal Investigation Directorate (an organisational unit of the General Police Directorate) or the Organised Crime Section, the General Crime section, the International Police Cooperation Section and the Criminal/Technical Investigations Centre.

3.2 Alignment with the acquis and planned measures

The organisation and method of carrying out border checks and state border protection measures are set out in the Border Control Act (OJ RS, No. 1/91). The method of carrying out border checks and state border protection measures are set out in the Regulations on the implementation of the Border Control Act (OJ RS, No. 19/91).

Article 3 of the 1998 Police Act (OJ RS, No. 49/98 and 66/98) defines the functions of the police. These include: 'protection of the state border and the effecting of border controls (5th indent), 'undertaking tasks specified in the Aliens Act' (6th indent) and 'undertaking tasks specified in this and other statutes and non-statutory regulations' (9th indent). Under the provisions of Article 4 of the Police Act these tasks shall be undertaken by the police, which comprises the General Police Directorate, police Directorates (at the regional level) and police stations. Internal organisation and the systematisation of human resources is set out in the Regulations on internal organisation and the systematisation of posts within the Ministry of the Interior and the Police.

The 'general' police powers defined in the Act include two powers important for the work of the police in controlling state borders: the power to establish identity and the power to order police surveillance of an alien during his stay in the country in specific cases and in accordance with statute. The method of implementation and use of individual police powers are set out in the Regulations on Police Powers (OJ RS, No. 51/00) issued by the Minister of the Interior. A 'Strategy for Undertaking Police Operations on the State Border' was adopted in 1996.

As part of the process of harmonising the legislation of the Republic of Slovenia with that of the European Union a new Aliens Act was passed in 1999 (OJ RS, No. 61/99). This Act sets out the conditions for aliens entering and leaving the country, the conditions for aliens residing in the country, leaving the country and cancellation of residence, procedures for the deportation of aliens, visas, the collection and protection of personal data, travel documents and permits, integration of aliens, registering and de-registering a place of residence, and records. The sections of the Aliens Act which define police border control operations, the protection of the state border and the prevention of illegal migration are to a large extent in line with the acquis (including the provisions of the Schengen Acquis).

In January 2001 the Instruction on the refusal of entry to an alien, conditions for issuing visas at border crossing points, conditions for issuing visas on humanitarian grounds and the method of cancelling a visa (OJ RS, No. 2/01) entered into force. This Instruction, issued on the basis of the provisions of the Aliens Act, recapitulates the provisions of the Schengen Acquis governing police border control operations. They define the method of establishing conditions for entry into the country and the reasons for refusing entry to an alien, the reasons for issuing a visa at border crossing points and the method of cancelling a visa during border checks.

The provisions of the Schengen acquis not recapitulated in the Republic of Slovenia's existing legislation will be adopted and defined in several documents:

- the new Border Control Act will mainly contain provisions defining the state border, control of the state border and the bodies responsible for effecting this control, crossing the state border and border crossing points, checks at the border and the setting up of certain registers. The National Programme for the Adoption of the Acquis by the end of 2002 envisages the passing of this Act by 30 June 2002;

- within the framework of the planned changes and additions to the Police Act will be more detailed definitions of the provisions on police powers to undertake operations abroad and of foreign police to undertake operations within the territory of the Republic of Slovenia, which will enable the implementation of the provisions on police cooperation contained in the Schengen Convention;

- the concept of organisation of police work must adapt itself to new tasks in the exercising of police control of the state border, above all in the implementation of 'adjustment' measures. As a result of the establishing of new police units and the gradual increase in the number of police officers, changes to acts on the systematisation and organisation of police work are planned;

- the preparation of a draft agreement and the putting into effect of agreements on police cooperation with neighbouring EU Member States (the provisions of Articles 39, 40 and 41 of the Schengen Convention) represent a further programme obligation;

- the set of preparations for the adoption of the Schengen acquis includes a definition of police cooperation with the Republic of Croatia. An agreement on police cooperation represents an obligation because the Slovene-Croatian border will also be the future external border of the European Union.

| Task | - Deadline | - Body responsible |
| --- | --- | --- |
| - Preparation of a new Border Control Act | - 30.6.2002 | - Ministry of Interior (MoI) in cooperation with twinning partners |
| - Law on modifications and amendments to the Police Act | - 30.6.2002 | - MoI |
| - Draft of changes and additions to (non-statutory) regulations on the systematisation and organisation of police work | - 31.12.2001 | - MoI (Police) |
| - Draft of model agreement on cooperation with neighbouring EU Member States across internal borders | - 31.12.2001 | - MoI in cooperation with twinning partners |
| - Review of alignment of bilateral agreements with Member States with the Schengen acquis | - 2001 – 2002 | - MoI in cooperation with twinning partners |
| - Conclusion of cooperation agreements on the basis of Schengen criteria with neighbouring EU Member States | - 2002 - 2004 | - MoI in cooperation with Ministry of Foreign Affairs (MFA) |
| - Gradual implementation of cooperation agreements on the basis of Schengen criteria with neighbouring EU Member States | - 2002 - 2005 | - MoI |
| - Preparation of draft agreement on police cooperation between the Republic of Slovenia and the Republic of Croatia | 2001 | MoI |

3.3 Organisation and personnel structure for the implementation of state border control

In planning the work of the police in the sphere of border control and protection of the state border the geographical dimensions of the area, the historically and socially conditioned uniform organisation and management of the police and the form of organisation set out in the new Police Act have been taken into account. We also proceeded from the following assumptions:

- that the border of the European Union on the Republic of Slovenia's accession to the European Union will be the state border with the Republic of Croatia. In the case of the Republic of Hungary not simultaneously becoming a member of the European Union and commencing the implementation of the Schengen acquis, the external border will also be the state border with the Republic of Hungary

- that the internal border of the European Union will be the state border of the Republic of Slovenia with the Republic of Italy and the Republic of Austria, and in the case of simultaneous accession to the European Union and the implementation of the Schengen acquis by the Republic of Hungary, the state border with the Republic of Hungary.

The organisational structure of the police does not include an independent or special border police division. Police units and police officers undertaking operations relating to border control and aliens are part of a uniformly-organised police force. The organisation of 'border police', like that of the police force as a whole, is at three levels – local, regional and national. Past analysis of the existing situation shows that possible differences between the organisation of border police in EU Member States and the Republic of Slovenia do not affect the efficiency of police operations. Even the new organisation of the police envisages administration at three organisational levels in the sphere of state border control. These are: in accordance with Schengen standards for the future external border of the European Union, for the future internal border of the European Union, and for the interior of the country. The organisational/personnel structure therefore proceeds from the existing form of organisation with slight adaptations. Planned organisational/personnel tasks include the following:

| Task | Deadline | Responsible body |
| --- | --- | --- |
| - Definition of organisation/personnel structure of police work according to Schengen standards | - 2000 | - MoI - Police, - twinning partners |
| - Analysis of personnel needs and preparation of personnel projection | - January - 2001 | - MoI – Police |
| - Provision of additional funding for increased employment | - 2001-2005 | - MoI – Police |
| - Running procedures for the employment of police officer candidates | - 2001-2004 | - MoI – Police |
| - Allocating students and police officer candidates to police units with regard to the projection and needs | 2001-2005 | MoI – Police |

On the basis of analysis of the pros and cons of the existing organisational and personnel structure of the police as a whole, specific analysis within the sphere of state border control, and calculation of future personnel requirements according to Schengen criteria and actual employee structure, a personnel projection up to 2005 was prepared in January 2001. This projection incorporated both employment strategy and the time required for the professional training of new police officers. Our two main starting points were the following:

- the number of police officers must guarantee that control of the state border and adjustment measures on the future external and internal borders and within the Republic of Slovenia can be carried out effectively when the Schengen acquis enter into force;

- an estimate of the personnel requirements of the police as a whole. Conceptually the police is uniformly organised and managed, something which is also reflected in the area of training, in new employment and in internal personnel movements.

A comparison of the number of police officers (uniformed police and criminal investigation officers) required to effect state border control to 'Schengen' standards and the existing employee structure and systematisation show that:

- at the beginning of 2001 there were 7036 systemised posts for uniformed and non-uniformed police officers, of which 6715 were occupied. Of the total number of unoccupied posts, 222 were for uniformed police and 99 for non-uniformed police;

- as at 1 January 2001 there were 1386 systemised posts for state border control operations (uniformed police officers);

- the difference between the existing systemisation of posts for state border control operations and the required new systemisation shows that it will be necessary to employ 1566 new police officers, at the local level (police stations), the regional level (police directorate border control and aliens groups at police directorates) and the national level (General Police Directorate).

In calculating the required number of positions we also have to take into acount the fluctuation of employees (police officers) up to 2005. On the basis of earlier trends we estimate that personnel fluctuation in the police up to 2005 will range from 1% to 2% (from 80 to 120 uniformed and non-uniformed officers leaving the service each year). On the basis of this estimate we predict that 413 officers will leave the police force by 2005.

Given that in estimating total personnel requirements up to 2005 we have taken into account all the elements defined above, we would need to employ 1887 new police officers over the next four years and 413 because of personnel fluctuation up to 2005. In 2000 the Ministry of the Interior began the gradual implementation of a personnel plan designed to achieve more effective control of the state border and to meet Schengen standards. In this context the Ministry employed 363 police officer candidates (174 were assigned to border units on the future external border) and 117 graduates of the Police College (30 were assigned to border units).

In order to realise the entire plan we will rely on: employing candidates from the labour market, employing graduates of the Police College, transferring police officers between police units, transferring customs service employees to police directortates and police stations from future internal borders (Austria, Italy), and the employment of contract staff for tasks not linked to the exercising of police powers.

On the border with the Republic of Croatia state border control is carried out by eight (8) police directorates, with direct border control being carried out by 29 police units. In accordance with the plan these tasks should in the future be carried out by 40 police units (11 more than at present), staffed by a total number of 3269 officers (1887 more than at present). The tables below show the existing situation and the proposed situation at all eight police directorates undertaking state border control operations on the future external border of the European Union, and for each directorate separately.

Overall situation:

| Existing situation |  |  | Proposal |  | Difference |  |
| --- | --- | --- | --- | --- | --- | --- |
| Police Directorate | No. of units | No. of officers | No. of units | No. of officers | No. of units | No. of officers |
| Koper | 6 | 353 | 7 | 568 | 1 | 215 |
| Postojna | 3 | 145 | 4 | 362 | 1 | 217 |
| Ljubljana | 2 | 86 | 2 | 197 | 0 | 111 |
| Novo mesto | 4 | 153 | 6 | 436 | 2 | 283 |
| Krško | 4 | 228 | 5 | 537 | 1 | 309 |
| Celje | 2 | 132 | 4 | 333 | 2 | 201 |
| Maribor | 6 | 172 | 7 | 506 | 1 | 334 |
| Murska Sobota | 2 | 113 | 5 | 330 | 3 | 217 |
| Total | 29 | 1382 | 40 | 3269 | 11 | 1887 |

KOPER

| Existing situation |  |  | Proposal |  |  | Difference |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Unit/ Directorate | No. of units | No. of officers | Unit/ Directorate | No. of units | No. of officers | No. of units | No. Of officers |
| PP Piran | 1 | 57 | PP*Piran | 1 | 85 | 0 | 28 |
| PMP Sečovlje | 1 | 56 | PMP Dragonja | 1 | 81 | 0 | 25 |
| PP Koper | 1 | 89 | PP* Koper I | 1 | 111 | 0 | 22 |
|  |  |  | PP* Koper II | 1 | 129 | 1 | 129 |
| PMP Škofije | 1 | 53 | PMP Sočerga | 1 | 68 | 0 | 15 |
| PMP Kozina | 1 | 58 | P(M)P Kozina | 1 | 32 | 0 | -26 |
| PPOP Koper | 1 | 40 | PPOP Koper | 1 | 62 | 0 | 22 |
| Koper | 6 | 353 | Koper | 7 | 568 | 1 | 215 |

POSTOJNA

| Existing situation |  |  | Proposal |  |  | Difference |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Unit/ Directorate | No. of units | No. of officers | Unit/ Directorate | No. of units | No. of officers | No. of units | No. of officers |
| PP* Ilir. Bistrica | 1 | 54 | PMP* Starod | 1 | 106 | 0 | 52 |
|  |  |  | PP* Ilir. Bistrica | 1 | 107 | 1 | 107 |
| PMP Jelšane | 1 | 51 | PMP Jelšane | 1 | 82 | 0 | 31 |
| PP* Cerknica | 1 | 40 | PP* Cerknica | 1 | 67 | 0 | 27 |
| Postojna | 3 | 145 | Postojna | 4 | 362 | 1 | 217 |

LJUBLJANA

| Existing situation |  |  | Proposal |  |  | Difference |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Unit/ Directorate | No. of units | No. of officers | Unit/ Directorate | No. of units | No. of officers | No. of units | No. Of officers |
| PP* Ribnica | 1 | 35 | PP* Ribnica | 1 | 73 | 0 | 38 |
| PP* Kočevje | 1 | 51 | PP* Kočevje | 1 | 124 | 0 | 73 |
| Ljubljana | 2 | 86 | Ljubljana | 2 | 197 | 0 | 111 |

NOVO MESTO

| Existing situation |  |  | Proposal |  |  | Difference |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Unit/ Directorate | No. of units | No. of officers | Unit/ Directorate | No. of units | No. of officers | No. of units | No. Of officers |
| PP* Črnomelj | 1 | 38 | PMP Vinica | 1 | 35 | 0 | -3 |
|  |  |  | P(M)P* Črnomelj | 1 | 105 | 1 | 105 |
| PMP* Metlika | 1 | 50 | PMP Metlika | 1 | 85 | 0 | 35 |
|  |  |  | PP* Metlika | 1 | 128 | 1 | 128 |
| PP Novo mesto | 1 | 53 | PP* Novo mesto | 1 | 60 | 0 | 7 |
| PO Šentjernej | 1 | 12 | PP* Šentjernej | 1 | 23 | 0 | 11 |
| Novo mesto | 4 | 153 | Novo mesto | 6 | 436 | 2 | 283 |

KRŠKO

| Existing situation |  |  | Proposal |  |  | Difference |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Unit/ Directorate | No. of units | No. of officers | Unit/ Directorate | No. of units | No. of officers | No. of units | No. of officers |
| PP Krško | 1 | 47 | PP* Krško | 1 | 74 | 0 | 27 |
| PP* Brežice | 1 | 61 | PP* Brežice I | 1 | 90 | 0 | 29 |
|  |  |  | PP* Brežice II | 1 | 123 | 1 | 123 |
| PMP Obrežje | 1 | 56 | PMP Obrežje | 1 | 135 | 0 | 79 |
| PMP Dobova | 1 | 64 | PMP Dobova | 1 | 115 | 0 | 51 |
| Krško | 4 | 228 | Krško | 5 | 537 | 1 | 309 |

CELJE

| Existing situation |  |  | Proposal |  |  | Difference |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Unit/ Directorate | No. of units | No. of officers | Unit/ Directorate | No. of units | No. of officers | No. of units | No. of officers |
| PP* Šmarje pri J. | 1 | 61 | PP* Šmarje pri J. | 1 | 95 | 0 | 34 |
| PMP* Rog. Slat. | 1 | 71 | PMP* Rog. Slat. | 1 | 110 | 0 | 39 |
|  |  |  | PMP Dobovec | 1 | 77 | 1 | 77 |
|  |  |  | PMP Bistrica/Sotli | 1 | 51 | 1 | 51 |
| Celje | 2 | 132 | Celje | 4 | 333 | 2 | 201 |

MARIBOR

| Existing situation |  |  | Proposal |  |  | Difference |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Unit/ Directorate | No. of units | No. of officers | Unit/ Directorate | No. of units | No. of officers | No. of units | No. of officers |
| PO Podlehnik | 1 | 15 | PP* Podlehnik | 1 | 45 | 0 | 30 |
| PMP Gruškovje | 1 | 37 | PMP Gruškovje | 1 | 102 | 0 | 65 |
| PMP* Zavrč | 1 | 34 | PMP Zavrč | 1 | 68 | 0 | 34 |
|  |  |  | PP* Gorišnica | 1 | 60 | 1 | 60 |
| PP* Ormož | 1 | 36 | PP* Ormož | 1 | 111 | 0 | 75 |
| PMP Središče | 1 | 35 | PMP Središče | 1 | 91 | 0 | 56 |
| PO Rače | 1 | 15 | PP* Rače | 1 | 29 | 0 | 14 |
| Maribor | 6 | 172 | Maribor | 7 | 506 | 1 | 334 |

MURSKA SOBOTA

| Existing situation |  |  | Proposal |  |  | Difference |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Unit/ Directorate | No. of units | No. of officers | Unit/ Directorate | No. of units | No. of officers | No. of units | No. of officers |
| PP* Ljutomer | 1 | 44 | PP* Ljutomer | 1 | 75 | 0 | 31 |
| PP* Lendava | 1 | 60 | PP* Lendava | 1 | 125 | 0 | 65 |
|  |  |  | PP* Črenšovci | 1 | 47 | 1 | 47 |
|  |  |  | PMP Petišovci | 1 | 60 | 1 | 60 |
| Police Unit (DUP) |  | 9 | PPVSPK Petanjci | 1 | 23 | 1 | 14 |
| Murska Sobota | 2 | 113 | Murska Sobota | 5 | 330 | 3 | 217 |

In planning the dynamics of employment we are also planning the training of new police officers up to 2005, where we mainly envisage employing graduates of the Police College (235) and police officer candidates (2065 candidates from the labour market). For cadets (graduates of the Police College) police officer training lasts 6 months. For candidates it lasts 18 months. The last new recruitment for the purposes of implementing this plan will take place in 2004.

|  | 2001 |  | 2002 |  | 2003 | 2004 | Total |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Training structure | Cadets | Candidates | Cadets | Candidates | Candidates | Candidates |  |
| Number | 120 | 455 | 115 | 585 | 540 | 485 | 2300 |
| Total | 575 |  | 700 |  | 540 | 485 | 2300 |

As a priority new police officers will be assigned to the police stations which will carry out border checks and state border control on the future external Schengen border. For this reason all cadets and police officer candidates employed in 2001 and 2002 will be assigned to existing and newly organised border units. In 2003 and 204 more vacancies at the regional and national levels will be occupied.

The significant increase in the number of police officers carrying out tasks relating to the protection of the future external border of the European Union will mean a need to provide larger premises at police stations, particularly at the local level. Related tasks include:

| Task | Deadline | Responsible body |
| --- | --- | --- |
| - Preparation of a plan for the design of new police units and identification of construction requirements | - 2001 | - MoI – Police |
| - Preparation of investment plan for the building of additional police facilities | - 2001 | - MoI – Police |
| - Implementation of investment plan | - 2002-2005 | - MoI |

3.4 Education and training

In 1998 a new vocational education programme for police officers was adopted. The programme is also aimed at adult candidates who have graduated from secondary school. On 1 January 1999 the first generation of adult candidates enrolled in the programme and enrolment at the Police College was abolished.

Given that the implementation of the provisions of the Schengen acquis requires a larger number of police officers, and in the light of the projection of employment in the police, the next few years will see the following education dynamics:

|  | - 2000 | - 2001 | - 2002 | - 2003 | - 2004 | - 2005 |
| --- | --- | --- | --- | --- | --- | --- |
| - School: - Cadets - Candidates | - 227 | - 360 | - 450 | - 465 | - 410 | - 150 |
| - To work: - Cadets - Candidates | - 117 - 71 | - 123 - 224 | - 115 - 360 | - 450 | - 430 | - 410 |
| - Total | - 188 | - 347 | - 475 | - 450 | - 430 | - 410 |
| - Total up to 2005: |  |  |  |  |  | - 2300 |

The following tasks were carried out in 2000 for the needs of education and training:

- A Police Academy was founded and the first generation began education (32 police officers);

- the subject ‘Border Issues and Aliens’ was made part of the curriculum of the Police Academy (60 hours in the first year, 156 hours in the second year as an optional subject);

- as part of the ‘twinning’ project a current state analysis was carried out and on its basis material relating to EU and Schengen acquis was incorporated into the syllabus;

- provision of the necessary number of specialised teachers and training for the same (3 in other countries and 30 in Slovenia with the assistence of experts from Germany and Austria as part of the twinning project, training of trainers to teach adults);

- part of the boarding accommodation was adapted for adults, classrooms were modernised and equipped to meet the needs of adults;

- current state analysis was carried out, the contents of European and Schengen legislation recorded and a curriculum drawn up for three target groups (border control, protection of the state border and protection of the internal border);

- a training concept for the needs of the police when establishing the Schengen external border was drawn up; spatial capacities for training at the local and regional levels were recorded and a training programme for trainers was drawn up;

- the contents of the EU acquis were incorporated into the syllabus of the College of Police and Security Studies, an associate member of the University of Ljubljana;

- the Academy of Administration is running special programmes on proffessional training in the organisation and legislation of the European Union and an independent module on ‘justice and home affairs’.

Tasks as part of the twinning project (2) relating to state border control:

| - Task | - Deadline | - Responsible body |
| --- | --- | --- |
| - Three training sessions for trainers | - January-March 2001 | - MoI - Police, - Police Academy |
| - Training of police management personnel | - January - 2001 | - MoI – Police |
| - Training of management personnel at local and regional levels | - March-April 2001 | - MoI - Police, Police Academy |
| - Evaluation of training of trainers | - June - 2001 | - MoI - Police, - Police Academy |
| - Training of 3 teachers abroad | - March - 2001 | - MoI – Police |
| - Training of 25 teachers – with the assistence of experts from Germany and Austria | - June - 2001 | - MoI – Police |
| - Definition of areas of police cooperation | - 2001 | - MoI – Police |
| - Training for police cooperation | - 2001 | - MoI – Police |

- Planned tasks and education and training plan, 2001-2005:

| - Task | - Deadline | - Responsible body |
| --- | --- | --- |
| - Cooperation on the design of a career system, effective method of recruiting and selecting new police officers | - 2002 | - MoI – Police, - Police Academy |
| - Ongoing monitoring of new elements in national, European and Schengen legislation and their incorporation into education programmes | - Ongoing task | - MoI – Police, - Police Academy |
| - Cooperation and exchange of experiences in the area of education with Member States | - Ongoing task | - MoI - Police, - Police Academy |
| - Drawing up training concepts at the central, regional and local levels, cooperation and competences | - May 2002 | - MoI - Police, Police Academy, - Police Directorates |
| - Financial evaluation of education of new police officers, students at the Police College and training programmes | - 2002 | - MoI - Joint Services |
| - Modernisation of accommodation and classrooms for the needs of adults, the College for Police and Security Studies and training | - 2003 | - MoI - Police, - Police Academy, - Joint Services |
| - Designing a training programme for three target groups of police officers, preparation of uniform teaching material and teaching aids | - 2003 | - MoI - Police, - Police Academy, - Uniformed Police Directorate |
| - Additional training of trainers (also with the help of EU Member States) | - 2003 | - MoI - Police, - Police Academy |
| - Modernisation and equipping of training premises at the local and regional levels | - 2003 | - MoI - Joint Services, - Police Directorates |
| - Financial evaluation of the training of police officers | - 2003 | - MoI - Personnel Service, Joint Services |
| - Pilot training, evaluation and possible supplements to programmes | - 2003-2004 | - MoI - Police, Police Academy, - Police Directorates |
| - Training | - 2004-2005 | - MoI - Police, Police Academy |
| - Monitoring training and evaluation | - 2005 | - MoI - Police, Police Academy, - Police Directorates |

3.5 Information - telecommunications system and the setting up and operation of the Schengen Information System

(Annex 1.5)

Owing to the great importance of the Schengen Information System (SIS), or rather to ensure the successful meeting of Schengen conditions, the twinning project for the protection of the state border included the formation of a special information/telecommunications (IT) project sub-group. With the assistence of experts from Austria and Germany this sub-group carried out an analysis of the current state of the police IT system and defined the steps necessary for entry into the SIS. Activities relating to the preparation of the police IT infrastructure for Schengen are also continuing within the context of the continuation of the twinning project on state border control.

The tasks which need to be realised for inclusion in the common Schengen Information System can be divided into several groups (detailed implementation of all the planned projects is provided in the annex):

- setting up (designing) the SIS;

- setting up a technical assistance unit (SIRENE);

- putting the SIS into operation.

3.5.1 Setting up of the Schengen Information System (SIS) and its operation

This task involves the setting up of a national SIS (N-SIS) and linking it to the central SIS (C-SIS). Current technical conditions do not enable the implementation of a SIS for candidates for entry to the European Union – even after the renovation of the system carried out in 1999.

As regards the coordination of data, analysis of the necessary conversions of data formats and definition of the interface for communication between the police information system and the N-SIS are a current priority. This task will probably be carried out within the context of the twinning project.

Special attention needs to be devoted to ensuring the reliable operation of the system. This applies both to the national information system and the SIS. Each individual Member State is responsible for the operation of its N-SIS. The maximum permitted time for resolving a malfunction is 6 hours, after which the country is excluded from the system. For this reason a special function known as ‘host backup’ has been defined. This will be analysed in detail as part of the twinning project.

3.5.2. Setting up of a technical assistance unit (SIRENE)

From the IT point of view communication with the technical assistance unit (Supplementary Information Request at the National Entry - SIRENE) will be planned together with the technical solution for communication between the national and central parts of the SIS (N-SIS and C-SIS). Currently communication is via an X.25 network and the X.400 message transfer protocol. This year however the system will switch to communication via an IP network – the SISNET project.

Despite the fact that the SIRENE office only gains a functional sense when the provisions of the Schengen acquis begin to be applied, the Slovenian Police decided to start gradual preparations of conditions for setting up this office during the first phase of preparations for membership of the European Union. The reason for this was to allow enough time for the verification of necessary adaptations to regulations, the planning of personnel structure, training, technical resources and information/telecommunications support, and also incorporating the role and function of the SIRENE office into international police cooperation (in connection with the activity of the national Interpol office and incorporation into Europol).

| Task | Deadline | Responsible body |
| --- | --- | --- |
| - Verifying tasks and determining the organisation of the SIRENE office in the Republic of Slovenia | - 2000 | - MoI (Police) in cooperation with twinning partners |
| - Preparation of draft (non-statutory) organisational acts for the SIRENE office and the necessary forms | - 2001 | - MoI (Police) |
| - Preparation of a draft of the Slovenian contribution to the SIRENE Handbook | - 2001 | - MoI (Police) in cooperation with twinning partners |
| - Preparation for the setting up and operation of the SIRENE office | - 2002-2003 | - MoI (Police) in cooperation with twinning partners |
| - Founding of the SIRENE office | 2004 | MoI (Police) |

3.5.3 Application of the Schengen Information System

The efficient use of the SIS requires the establishing of suitable IT infrastructure which enables inquiries at the external border and checking within the SIS in the case of regular controls within the country. Given the established deficiencies of existing information/telecommunications infrastructure we have defined two projects designed to remove these:

- setting up or upgrading the access network

- setting up of local infrastructure (LAN).

The construction of access network infrastructure envisages project the provision of suitable connections between individual police units and police directorates. The existing SNA communications devices will be replaced by a router and capacity will be increased. The network will enable data transfer and voice communication (VoIP).

As part of the setting up of local infrastructure project, all police units will be equipped with a local area network (LAN) and corresponding active information equipment.

Both projects will be carried out in three phases. In the first phase we will limit ourselves to the future external border of the European Union, in the second phase we will equip units in the border area (green border) and in the third phase we will equip police units in the interior of the country. The timetable and deadlines for individual projects are shown in the table below.

| Task | # Phase | Completion deadline |
| --- | --- | --- |
| N.SIS and N.SIS–C.SIS communication |  | 2005 |
| Host backup |  | 2005 |
| Access network | 1 – external border | end of 2002 |
|  | 2 – border belt | end of 2003 |
|  | 3 – interior | 2005 |
| LAN infrastructure | 1 – external border | end of 2002 |
|  | 2 – border belt | end of 2003 |
|  | 3 – interior | 2005 |

The complete technical modernisation of the information/telecommunications system also includes plans for the gradual introduction of a digital radio system, replacing the existing analogue system. This will be based on European standards for this field and in this way we will ensure the possibility of international connectivity, above all within the context of police cooperation. The digital radio network will also facilitate high-quality data communication for the needs of mobile police units.

3.6 Technical equipment for the control of the future external border

In order to carry out effective control of the state border in accordance with the Schengen acquis we need to ensure that the Slovenian police force has all the appropriate technical equipment. Within the framework of the twinning project the types and quantities of equipment needed by the police to implement the Schengen acquis on the future external and internal borders have been defined in detail. In estimating the necessary equipment we have taken as a starting point the personnel projection for 2000-2005 and the currently valid Regulations on the systemisation of material/technical resources. We have defined the following types and quantities of necessary material/technical equipment:

- vehicles – motorcycles, cars, all-terrain vehicles, vans, lorries – a total of 323 different vehicles;

- vessels and aircraft – a patrol boat up to 15 metres long (1); a patrol boat up to 8 metres long (1); a helicopter capable of transporting up to 7 people and helicopter equipment (2);

- equipment for controlling the state border: equipment for checking documents permitting the crossing of the state border (‘Schengen’ stamps for border checks, devices for verifying the authenticity of documents), equipment for inspecting vehicles (devices for inspecting difficult-to-access parts of vehicles, CO2 detectors, etc.) and devices to forcibly halt vehicles;

- criminal investigation/technical equipment: equipment for dealing with criminal offences and persons (special suitcases containing the equipment necessary when visiting crime scenes, preliminary tests for narcotics, etc.);

- protective equipment: bulletproof jackets and helmets (bulletproof shirts and vests, bulletproof helmets)

- special technical equipment and aids: night-vision devices, thermovisual devices, special video systems for surveillance at border crossing points, detectors, topographic aids.

| Task | Deadline | Responsible body |
| --- | --- | --- |
| - Definition of type and quantity of equipment needed to meet Schengen standards | - 2000 | - MOI - Police with twinning partners |
| - Estimate of purchase costs | - 2000 | - MOI – Police |
| - Preparation of dynamics of equipment purchase | - 2001 | - MOI – Police |
| - Provision of necessary funds in the budget and within PHARE programmes | - 2001-2005 | - MOI – Police |
| - Realisation of annual purchase plans | - 2001-2005 | - MOI – Police |
| - Allocation of equipment according to plan and requirements | - 2001-2005 | - MOI - Police |
| - Analysis of use of equipment and effect of use and preparation of purchase plan for 2005 | - 2004 | - MOI – Police |

- Dynamics of planned purchases 2000-2005 (in %):

| ## TYPE OF EQUIPMENT | - Value in € | - 2000 | - 2001 | - 2002 | - 2003 | - 2004 | - 2005 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ##### VEHICLES | - 6,649,000 | - 0% | - 2% | - 18% | - 42% | - 30% | - 8% |
| - Vessels | - 713,200 | - 0% | - 0% | - 92% | - 8% | - 0% | - 0% |
| - Aircraft | - 9,260,000 | - 0% | - 0% | - 50% | - 50% | - 0% | - 0% |
| - BORDER CONTROL EQUIPMENT | - 2,644,900 | - 0% | - 30% | - 19% | - 23% | - 17% | - 12% |
| - CRIMINAL INVESTIGATION/ - TECHNICAL EQUIPMENT | - 653,800 | - 0% | - 0% | - 15% | - 38% | - 33% | - 14% |
| - PROTECTIVE EQUIPMENT | - 473,900 | - 0% | - 0% | - 25% | - 25% | - 25% | - 24% |
| - SPECIAL TECHNICAL EQUIPMENT AND AIDS | - 4,834,300 | - 0% | - 18% | - 20% | - 21% | - 31% | - 10% |
| ### TOTAL | - 25,229,100 |  |  |  |  |  |  |

The dynamics of purchasing equipment correlates closely to the dynamics of employment in the 2000-2005 period. Most of the vehicles, equipment for controlling the state border and protective equipment will therefore be purchased in 2003 and 2004. According to the plan the first helicopter should be purchased in 2002 and the second in 2003. Likewise the patrol boat should be purchased or delivered in 2003.

3.7 Specific measures at airports and sea ports

Slovenia has three airports handling international traffic. The central airport (Ljubljana-Brnik) meets the criteria for international airports, while the airports at Maribor and Portorož (doc. SCH/Com-ex [94] 17, 4. Rev.) fall into the aerodromes category. The provisions of the Schengen acquis require the physical separation of passengers on internal and external flights, which enables border controls to be carried out on external flights and adjustment measures to be taken on internal flights.

As part of the twinning project (special project sub-group) construction projects have been planned in cooperation with the airport operator in order to meet the Schengen criteria. The plans were endorsed by the director-general of the police and the chairman of the airport board has been officially informed of them.

The Aviation Act obliges airport operators to ensure conditions that enable the police to carry out their work at airports, and thus a suitable method of carrying out border controls. Under the provisions of the Border Control Act the consent of the Ministry of the Interior or the police must be obtained for all construction projects in the area of a border crossing point.

In the case of rapid growth in traffic at Ljubljana Airport a new terminal is expected to be built. Under the terms of the agreement reached with the chairman of the airport board, police representatives will cooperate in the planning of the new terminal and ensure that it meets Schengen border control standards.

Slovenia has three border crossing points for maritime traffic – two, at Piran and Izola (summer only) are for yachts and other tourist traffic, while the third is the border crossing at the Port of Koper. Within the context of the twinning project (special project sub-group) the method of implementing border control at sea ports and the protection of the state border at sea have been reviewed. It has been found that there are no major deviations from Schengen standards.

Measures relating to staffing levels at the Airport Police Station and the Maritime Police Station, and to their capacities and levels of equipment, are defined in the relevant chapters of the action plan.

| - Task | - Deadline | - Responsible body |
| --- | --- | --- |
| - Preparation of plans for adaptation of airports | - 2000 | - MoI (Police) with twinning partners and airport operators |
| - Adaptations of existing airport infrastructure | - 2005 | - Airport operators in cooperation with the MoI |
| - Preparation of plans for a new terminal at Ljubljana Airport which meets Schengen criteria | - As specfied in the plans of the airport operator | - Airport operators in cooperation with the MoI (Police) |
| - Review of the work of the police in border controls at sea ports from the point of view of Schengen standards | - 2000 | - MoI (Police) with twinning partners |

3.8 Measures at internal borders and within the country; police cooperation

In preparing the concept of the future work of the Slovenian police in the implementation of the Schengen acquis, great stress has been laid on the introduction of the measures that will be necessary following the abolition of checks at internal borders. This means the abandoning of stationary border checks (Article 2.1 of the Schengen Convention) and their replacement with police adjustment measures (Article 23 of the Schengen Convention), and the development of police cooperation (Articles 39 to 47 of the Schengen Convention), all of which requires changes in the organisation and tactics of police work. Measures have been prepared in cooperation with twinning partners in the two twinning projects.

Under the provisions of the Police Act regional police directorates have the function of cooperation with the security bodies of neighbouring states. On this basis a range of cooperation agreements relating to the protection of the border and border checks have been concluded with the security bodies of neighbouring states at the regional level. Slovenia has concluded the following agreements with neighbouring states:

- Austria: Protocol on envisaged measures for ensuring the flow of traffic at border crossing points (1996); Agreement on cooperation on border checks (1998);

- Italy: Memorandum on cooperation between the police forces of the Republic of Slovenia and the Italian Republic (1997); Agreement on cooperation between the police forces of the Republic of Slovenia and the Italian Republic (signed 5 July 1998);

- Hungary: Minutes on cooperation between the Police Administration of the Ministry of the Interior of the Republic of Slovenia and the State Border Guard Command of the Republic of Hungary (1994); Protocol between the Government of the Republic of Slovenia and the Government of the Republic of Hungary on joint measures in the carrying out of border checks at road border crossing points on the Slovenian-Hungarian state border (1995).

A major contribution to the strengthening of cooperation with the police forces of EU Member States in the area of state border control should come from long-term partnerships between certain units of the Slovenian police on the one hand and units in neighbouring and nearby EU Member States (e.g. the German Federal Border Guard or the Austrian Gendarmerie) on the other.

| Task | Deadline | Responsible body |
| --- | --- | --- |
| - Preparation of a concept of police work following the abolition of checks at internal borders and identification of needs | - 2000 | - MoI (Police) with twinning partners |
| - Preparation of a draft of the national part of police cooperation guidelines | - 2001 | - MoI (Police) in cooperation with twinning partners |
| - Preparation of the concept of cooperation across internal borders (contact points, communications officers, direct border-region cooperation, etc.) | - 2001 | - MoI (Police) in cooperation with twinning partners |
| - Drawing up a communications officers exchange programme | - 2002 | - MoI (Police) |
| - Planned strengthening of cooperation with police units in EU Member States | - 2001 - 2005 | - MoI (Police) in cooperation with twinning partners |
| - Gradual intensifying of cooperation with neighbouring countries for the purposes of approximation of Schengen standards | - 2001 - 2005 | - MoI, Police in cooperation with MZZ |
| - Preparation of plan for the removal of traffic barriers at internal borders | 2004 | Joint Services of the Government of the Republic of Slovenia in cooperation with other departments |

4. HARMONISATION OF THE VISA POLICY OF THE REPUBLIC OF SLOVENIA WITH SCHENGEN STANDARDS

(Annexes 1.6, 1.7, 1.8)

4.1 Harmonisation with the acquis communautaire

In compliance with the National Programme for the Adoption of the Acquis by the end of 2002, visa-free agreements with countries whose nationals require a visa to enter the EU Member States were terminated in 1999 and 2000 (Council Decision No. 574/99 of 12 March 1999). The Government of the Republic of Slovenia adopted a decision on complete harmonisation of the Slovene visa regime with that of the European Union in October 1998. In December 1999, the decision was fully implemented regarding the “black list”, whereas as regards the “white list”, the Republic of Slovenia has abolished visa requirements in respect of twelve countries (Bolivia, Brunei, Bulgaria, Costa Rica, Ecuador, El Salvador, Guatemala, Honduras, Nicaragua, Panama, Paraguay, and Venezuela) and of passport holders of special administrative regions of the People’s Republic of China (Hong Kong, Macau) in May 2001.

The Government of the Republic of Slovenia adopted the Decision on the Abolition of Visa Requirements for the countries listed above. With the adoption of the Decision, the visa regime of the Republic of Slovenia is completely harmonised with the visa policy of the European Union, i.e. Council Regulation (EC), No 539/2001 of 15 March 2001. The Government Decision of 16 March 2000 applies to citizens of Romania; the Decision stipulates that the visa regime concerning the citizens of Romania depends on the decision of the Council of the European Union. Pending the final decision of the Council of the European Union, visa regime in the Republic of Slovenia does not apply to the citizens of Romania.

In the Republic of Slovenia, the entry into, departure from and residence of aliens, and thus the visa regime, are governed by the Aliens’ Act (OJ RS, No. 61/99) which complies with the majority of requirements of the acquis communautaire. Last year, the following executive regulations relating to the said Act were adopted:

- the Instruction on the Content and the Format of the Visa (OJ RS, No. 450/00);

- the Instruction on the Refusal of Entry to an Alien, Requirements for Issuing a Visa at Border Crossings, Requirements for Issuing a Visa for Humanitarian Reasons and Modes of Cancellation of a Visa (OJ RS, No. 2/01).

The Republic of Slovenia has, to a great extent, also harmonised individual documents with safety and security standards defined in the acquis communautaire and/or in the Schengen acquis. In this context, the following has been put into effect: new passports, visa sticker (annex), residence permit sticker (annex) and a visa questionnaire (annex).

Passports of the Citizens of the Republic of Slovenia Act was adopted by the National Assembly on 20 June 2000 (OJ RS, No. 65/2000). The issuing of new Slovene passports started on 1 March 2001. In May 2000, the Instruction on the Content and the Format of the Visa, and the Instruction on the Content, Form, Mode of Issuing and Cancellation and/or Expiry of Residence Permit (OJ RS, No 45/00). The new visa stickers and residence permit stickers have been in use since 1 June 2000 and are completely harmonised with the safety and security standards as provided for in Council Regulation No. 1683/95 of 29 May 1995 laying down a uniform format for visas (OJ, L164/95) and with the standards defined in the Joint Action of the Council on a uniform format for residence permits of 16 December 1996 (OJ, L 7/97) and in Council Decision of 3 December 1998.

The Act provides for centralised issuing and personalisation of the ordinary, service and diplomatic passports and is completely harmonised with both the acquis communautaire and international standards governing the documents; at the same time, it ensures the upgrading of the existing passport forms as well as the information and logistic support to the procedures of issuing, making and distribution of passports in compliance with the safety and security standards and recommendations of the European Union. The passport will include several security features and a selection of the data boxes will be completely harmonised with the Resolution on a Uniform Format for Passports.

Consular instructions on the issuing of visas at diplomatic missions and consular posts of the Republic of Slovenia have already been prepared and implemented. They are harmonised with the Aliens’ Act and with the Common Consular Instructions of the Schengen states on the issuing of visas at the diplomatic missions and consular posts, with the exception of those provisions which may be implemented only after the accession to the EU, including the representation of the state responsible for deciding on applications for visas.

In 2000, the Republic of Slovenia participated in a twinning project with the Republic of Austria within the scope of the tasks for the adoption of the acquis communautaire and the institution building in this field. The aim of the project was to harmonise Slovene legislation, policy and practice concerning migration and consular practice, in particular with regard to visas. In the final report on the twinning project (December 2000), both countries drafted 58 recommendations defining guidelines for the preparation of legal regulations, organisational measures and practical procedures for the harmonisation with the European migration policy and practice. In the field of visa policy and practice, the main recommendations refer to:

- the need for the regulation and division of competencies of individual bodies concerning visa-related issues;

- defining the competencies of consular officers in visa procedures;

- defining communication channels and consultation mechanisms;

- the need to set up the VISION system (Master plan, see Annex);

- the need to recruit more staff in certain departments of the Ministry of Foreign Affairs;

- defining the procedures and content of security clearance of staff and

- providing security and technical standards of operation at foreign missions at an appropriately high level.

On the basis of the recommendations of the twinning project and practical experiences, a working group was established to prepare amendments to the Aliens Act, which is to provide the entire legal basis for visa procedures. In compliance with the National Programme for the Adoption of the Acquis by the end of 2002, the Act will have been probably adopted by 30 June 2002.

4.2 Education and Training

The Ministry of Foreign Affairs is carrying out, for the officers responsible for consular (visa) procedures, preliminary training prior to their departure to take up duties and also regular on-the-job-training. Each staff member who wishes to take up duties relating to visa procedures at a consular post (these posts require at least short-type higher education degree) has to, prior to his/her departure to take up duties at a consular post, complete a special training programme with particular emphasis on migration policy, consular work and cooperation with other missions on the spot and on the coordination of the contents and procedures.

At least once per year, the Ministry of Foreign Affairs organises consular consultations for all officers of the Slovene consular network. In addition, consultations on special topics are organised for individual regions or individual missions facing special or new tasks (changes in the migration trends, in visa policy, or in technical working bases).

Within the scope of the twinning project, attention was partly devoted to education, seventeen (17) seminars and consultations were organised, which were attended by over seventy (70) staff members of the Ministry of Foreign Affairs. We have also introduced practical cooperation, in which Slovene training programmes also include lectures of certain experts in consular issues from the Member States, and Slovene consular officers are invited to attend consultations and training organised by the Member States.

4.3 Visa Information System

All Slovene diplomatic missions and consular posts have an on-line connection with the electronic information system the central point of which is the Ministry of Foreign Affairs. Slovenia has also established the VIZIS Information System (visa information system) as a support for visa procedures. This system performs all the functions required for the VISION application. The system allows for simple and quick verification of data on the applicants in the relevant records of the Slovene state administration, the application of data in decision-making on the issuing of visas, effective control of the issuing of visas, control of the data contained in the passport on crossing the border and financial control of operations. The VIZIS system functions as an information link between diplomatic missions and consular posts , the Ministry of Foreign Affairs and the Ministry of the Interior. At the same time it allows for a high technical and quality level of visa stickers issued. According to the assessment of experts (in the Twinning project) the information system is in compliance with all technical standards required and applied by the European Union.

The information system for visa operations includes several modules performing different functions. It allows for: entry of data from an application, their unification through coders and logical control; printing of visa stickers and their control or tracing starting with the sticker manufacturer, and proceeding from the Ministry of Foreign Affairs, diplomatic missions and consular posts to an individual passport; verification of applicants in local control lists and records which are automatically renewed and updated; additional verification of applicants by the relevant services of the Ministry of Foreign Affairs and the Ministry of the Interior; keeping a logbook – data on applications and visas issued; automatic filing of obsolete data; following the income from visas issued and their automatic recording in the financial application; and elaboration of statistics and analyses (the course of the procedure - information channels - between the relevant authorities is evident from the table).

The VIZIS system is currently in operation at eight Slovene missions. Last year, this system was applied to more than a half (50%) of Slovene visa procedures. According to the timetable (Annex 5), the entire Slovene consular network will have been included in the VIZIS information system by the end of 2002. We also expect that the VISION application will be fully established by the time of Slovenia’s accession to the EU. The following steps were taken to launch the VISION application:

- all Slovene missions abroad have an on-line connection with the Ministry of Foreign Affairs;

- the central point for consular posts (MFA) set up the VIZIS information system which is being gradually upgraded;

- a link has been established between the MFA and MI, which is, in technical terms, of high quality and, in terms of contents, facilitates communication when using the VISION application;

- according to the agreed decision of the Ministry of Foreign Affairs and of the Ministry of the Interior, the central point for communication with Member States (the SIS, SIRENE and VISION functions) will be located at the Ministry of the Interior. Technical assistance for these preparations is provided by the European Union within the scope of the PHARE programmes.

- 4.4 Security standards for consular (visa) work

- The Slovene consular posts abroad provide the basic security and technical conditions. A programme has been developed, ensuring the required security and technical standards at all missions (special entrance for visa applicants, desk with bullet-proof screen, technical security of rooms and buildings, protection and storage of forms and documents, alarm in case of burglary or break-in) by the end of 2002.

5. IMPLEMENTATION OF SCHENGEN AGREEMENT PROVISIONS ON DATA PROTECTION

In 1994, the Republic of Slovenia ratified the Convention for the Protection of Individuals with regard to Automatic Processing of Personal Data  (Strasbourg 1981), which is directly used in the internal jurisdiction. In the Republic of Slovenia, protection of personal data is guaranteed also in the Constitution of the Republic of Slovenia (OJ RS, Nos. 33/91 and 42/97, Article 38). The new Personal Data Protection Act (OJ RS, No. 59/99) fully implements the provisions of the acquis, the provisions of the Convention and both directives (95/46/EEC and 97/66/EEC). The provisions of the Schengen agreement are already observed by the act although the Republic of Slovenia is not a member of the Agreement yet. The provisions of the act observe practically all requirements of the given documents except for the requirement of independent supervision of protection of personal data.

The role, the kind and the level of the responsibilities of independent institution of personal data protection will be determined by the Act on Modifications and Amendments to the Personal Data Protection Act. The Act will enable the establishment and operation of an independent institution of personal data protection. According to the Republic of Slovenia's National Programme for the Adoption of the Acquis by the end of 2002, the act will be adopted by 31 December 2001 at the latest.

The legislation of the Republic of Slovenia is not fully in line with the provisions of the agreement, especially with Article 114 which stipulates that each country names an independent institution to perform the supervision of personal data protection. Modifications and amendments to the Personal Data Protection Act, which are now being discussed by the Parliament, will ensure the establishment and operation of an independent institution of personal data protection. The Personal Data Ombudsman with his deputy will fully implement the requirements of this provision as an institution. The content of Article 115 of the Agreement will be also implemented by an independent institution of personal data protection.

In line with the amendment, the supervision of personal data protection will be ensured through the inspectorate of personal data protection, while the independent supervision of the implementation of the provisions of the Personal Data Protection Act will be ensured through the Personal Data Ombudsman, precisely through the Deputy Personal Data Ombudsman.

The Inspectorate for Personal Data Protection will be founded within the Ministry of Justice, which is responsible for the implementation of the Personal Data Protection Act. The Inspectorate will have the function of exercising inspection and supervision of legislation applying to the work of managers of collections of personal data, the catalogue of collections, etc. As part of this function, inspectors will be authorised to rectify established breaches of law. Slovenian legislation provides inspectors with independence and a permanent term in office. Legal protection is provided against the provisions of the inspectorate.

Given that the Inspectorate is part of state administration and that it supervises exclusively the lawfulness of operations by managers of collections of personal data, the amendments provide for the introduction of an independent institution for personal data protection: the Personal Data Ombudsman. The Personal Data Ombudsman will, in line with the amendment to the Act, be organised in the form of a special office and an independent budget user. The deputy Personal Data Ombudsman is appointed by the National Assembly following the proposal of the Personal Data Ombudsman. Once every year, the Personal Data Ombudsman reports to the Parliament on his findings, proposals and recommendations as well on the situation in the area of personal data protection.

Other provisions of Chapter 3 of the Agreement on the Implementation of the Schengen Convention "Protection and Insurance of Data in the Schengen Information System" are regulated in the above-mentioned Personal Data Protection Act and the Police Act together with secondary legislation adopted on the basis of these.

The requirement of Paragraphs 4 and 5 of Article 102, which stipulates that personal data may be used only for the legally stated purposes, is regulated by Article 9 of PDPA.

Recording of access to and use of personal data as required by Article 103 is regulated for national information systems by Article 13 of PDPA which requires the recording of any access. In the police information system this provision is concretised in Chapter VII of the Regulations on Police Data Protection. All these measures are being already implemented in practice. The same level of access control and recording is foreseen also for all data in the Schengen Information System.

Any individual has a right to be acquainted with the data contained in databases and referring to him or herself. Certain restrictions of this right necessary for the enforcement of Article 109 are enforced by Article 23 of PDPA. The restriction of the right to the access of data foreseen by Article 109 is stipulated also in Chapter IV of the Police Act.

Individuals may enforce their rights foreseen by Articles 110 and 111 of the Agreement on the basis of Articles 18, 19 and 20 of PDPA (supplement, correction or deletion of data and judicial protection of individual's rights).

The Republic of Slovenia enforced the provision of Article 116 of the Convention in the Personal Data Protection Act (Article 22), which stipulates the right of individuals (regardless of their citizenship and place of residence - Article 6 of PDPA) to require compensation if they suffered any damage due to any use of personal data referring to themselves and collected in the way or for the purpose not in line with the provisions of the Act. This provision and regulations allowing individuals in the Republic of Slovenia to enforce the compensation responsibility of the state when they suffered damage due to the conduct of state bodies are an appropriate background for the adoption of the responsibilities of the Republic of Slovenia for the use of the Schengen information system.

Provisions of Articles 117 and 118 and articles referring to data protection (Articles 126 to 130 of the Agreement) are already implemented at the level of national legislation. The basic content framework of personal data protection is stipulated by Article 13 of the Data Protection Act whose content encompasses a compulsory implementation of most safety measures foreseen by Article 118 of the Agreement. A more detailed regulation of the insurance of computer processing of personal data is provided by sector-specific instruments and regulations issued on the basis of these. For the police, the implementation of these measures is thus regulated in Chapter IV of the Police Act (OJ RS, No. 49/98) and in the Regulations on Police Data Protection (OJ RS, No. 79/99).

The Regulations stipulate that all personal data of the police is protected by special safety measures. The entrance to facilities where machines for personal data processing are installed is guarded so that unauthorised persons cannot enter (Article 9). In case of very important data the entry of all authorised users to the facilities where the data is processed or stored is recorded, too (Articles 9 and 10). Media in which data is stored are appropriately marked and recorded (Article 19). When they are not used or being directly controlled by an authorised user they are stored in safety iron closets or vaults (Article 21). The access to data, their entering, modifying and deletion are protected by the system verifying the identity of a user and his or her authorisation to access data (Article 16). Any form of data access – viewing, entering, modifying and deletion – is entered in the automatic system of control and recording of access (logbook or journal), which enables a subsequent identification of the user dealing with the data in a given time from a given terminal, workstation or other information device (Article 17). The reconstruction of accesses is possible for the period for which the data are kept (at the moment it is possible to reconstruct all accesses to data in police records since 1994). All written communication of data is recorded in line with the regulations of office management. The transfer of certain personal data through telecommunication networks – these include the data from the records of police and judicial authorities – has to be crypto protected and insured by electronic signature (Article 4 of PDPA and Article 30 of the Regulations), while letter consignment of these data have to be protected with appropriate safety mechanisms or transferred through a courier.

All described measures are already implemented in practice and will be included in the National Schengen Information System or in the connection of the national with the central Schengen system.

| Task | Deadline | Implementing Agency |
| --- | --- | --- |
| - Act amending the Personal Data Protection Act | 31 December 2001 | Ministry of Justice |
| - Confidential Data Act | 30 June 2001 | MoI |
| - Appointment of Persons Responsible for Independent Supervision in the Framework of Schengen Agreement Provisions | 2004 |  |
| - Introduction of electronic signature in the police e-mail | 2002 | MoI – Police |
| - crypto protection of data connections to all police stations of the third level (police stations, interstate border crossings) | 2001 - 2005 | MoI – Police |
| - the modernisation of the automatic control system and the recording of the access to police records and other services of police information system | 2002 | MoI – Police |
| - the introduction of the single sign-on system in the police information system | test 2001, introduction 2003 | MoI – Police |
| - the introduction of the system of remote control and diagnosing of all elements of police information system | test 2001, introduction 2003 | MoI – Police |

All employees of the information – telecommunication police service and other persons competent for management and maintenance of software and hardware and the data of police information service have to undergo a security check (Article 67 of the Police Act and Article 3 of the Regulations) and be qualified to operate this equipment and data respectively (Article 13). If these services include external providers these persons have to undergo a safety check too, providing a written verification that they are acquainted with the rules of data protection in the police information system.

The procedures of safety check of persons having an access to certain data in central authorities will be regulated by the Confidential Data Act in a detailed way uniform for all central authorities. At the moment the Act is undergoing the second reading in the national Assembly, with its practical implementation foreseen in the second half of 2001. Since most of personal data referred to in the framework of the Schengen Information System are confidential due to their importance in the implementation of tasks of state bodies and the damage caused by the access of non-authorised persons to them, the Confidential Data Act will provide a more elaborate regulation of some security standards significant for the implementation of Articles 117 and 118 of the Agreement on the Implementation of Schengen Convention.

Transfer of personal data from the Republic of Slovenia and their provision to foreign users is allowed only if the country into which the data are transferred has a regulated personal data protection in line with the Convention for the Protection of Individuals with regard to Automatic Processing of Personal Data (convention No 108 as of 28 January 1981). Data provision has to be regulated by an international contract, convention or agreement. Any transfer of personal data from the country has to be recorded (Article 24 of PDPA).

Personal data dealt with by central authorities, therefore also the data of the Schengen Information System, can be collected, processed, used, stored and transferred only on the basis of a legal authorisation and for purposes stipulated by legislation (Article 3 of PDPA).

The supervision of personal data dealt with in the framework of the national SIS or exchanged with the central SIS, will be implemented by the central body of the supervision of personal data protection, established at the end of 2001 on the basis of the changes and amendments of the Personal Data Protection Act. It means that this common national supervision body will be authorised to implement all tasks foreseen by the Convention.

6. TECHNICAL ASSISTANCE OF THE EUROPEAN UNION AND FINANCIAL REALISATION PROGRAMME FOR SETTING UP CONTROL ON THE FUTURE EXTERNAL BORDER OF THE EUROPEAN UNION

6.1 Technical Assistance of the European Union in Implementing the Strategy  Contained in the Chapter »Justice and Home Affairs«

The Ministry of the Interior is fully aware of the necessity to train its employees to implement the tasks in the area of homr affairs, as well as of necessary investments to update technical equipment in the control of the future external border of the European Union. Namely, the Schengen acquis sets extremely high standards of border control and external border protection, and requires staff with adequate expert qualifications. This activity takes place either on the basis of bilateral agreements between the police forces of the EU Member States or on the basis of the national Phare programme and other programmes of the European Union.

With the preparation of strategic documents (Accession Strategy) and The Republic of Slovenia's National Programme for the Adoption of the Acquis by the end of 2002 in the area »Justice and Home Affairs«, Slovenia in 1997 entered also the national Phare programme and was granted resources amounting to 0,3 million EUR. Resources granted to Slovenia amounted to 4,25 million EUR in 1999; 6,12 million EUR in 2000; resources planned in the programme for 2001 amount to 6,0 million EUR. In addition, technical assistance is planned for 2002 and 2003 in the framework of the programme. The resources in Phare framework are intended for institution building and investments in technical equipment and objects.

Institution building takes place in the form of »twinning« projects, or as a form of assistance of a partner country to a candidate country in the process of adaptation to the European Union. In the entire area of »justice and home affairs«, the framework of the Phare programme plans seven (7) »twinning« projects, namely: five (5) programmes in the areas belonging to the Ministry of the Interior, one (1) in the competence of the Ministry of Justice (organisation, operation and education in justice), while one project will be implemented within the Drug Office of the Republic of Slovenia (prevention of drug addiction). All these projects are or will contribute to harmonisation of legislation, a more efficient operation of justice system, training, institution building and the preparation of an action plan to implement the provisions of the Schengen Agreement, the strategy of prevention and control of organised crime and the national programme in the area of drugs.

In the framework of the Ministry of the Interior, one twinning project is being implemented while two are already finished. These three projects are from the following areas:

- the area of control of the state border; begun on 1 September 1999 and finished at the end of August 2000 (partner countries Germany and Austria);

- the area of migration (with the co-operation of the Ministry of Foreign Affairs); begun on 1 January 2000 and finished on 31 December 2000 (partner country Austria);

- the area of the state border control: a new project with the same partner countries, representing an upgrade of the first twinning project, was begun on 1 September 2000. It will be finished on 31 August 2001.

Further twinning projects are being prepared in the following areas:

- organised crime, together with the Ministry of Justice (partner countries Italy and Spain), whose launching is foreseen in May 2001 and completion at the end of April 2002;

- in 2002, a similar project is planned also in the area of police co-operation  (partner country Spain). Its launching is foreseen in March 2002 and its completion in February 2003.

The framework of the Phare 1999 programme foresees also the programme of investments in information (2,18 million EUR) and technical equipment (1,12 million EUR) amounting to 3,3 million EUR from the total amount of 4,25 million EUR approved in 1999, with an equal or bigger contribution from the budget of the Republic of Slovenia. For this purpose the entire public tender documentation was prepared and confirmed by an independent expert from the European Commission, a positive opinion of the Central Financial and Contracts Unit of the Ministry of Finance and an approval of the Delegation of the European commission in Ljubljana were acquired, a public tender was published in the EU and RS Official Journals, providers were chosen.

From the rest of resources, after providers were chosen, a proposal for reallocation of resources (from the total amount of about 270.000 EUR) was prepared, and 123.000 EUR were intended for twinning in the area of organised crime where it was established at the preparation of the contract that the resources are not sufficient. The proposal was confirmed by the Government Office of European Affairs, Central Finance and Contracts Unit, and the Delegations of the European Commission in Ljubljana. Also prepared is the tender documentation for investments from the remaining resources amounting to approximately 149.000 EUR.

The Phare 2000 programme foresees the assistance amounting to 6,12 million EUR. The amount intended for investments in information and telecommunication equipment is 3,28 million EUR; that for technical equipment for control of state border amounts to 2,54 million EUR, while the assistance intended for the twinning project is 0,3 million EUR. Furthermore, the share of resources from the budget of Slovenia, amounting to 7, 6 million EUR, has to be observed. The National Phare programme for 2000 was confirmed by a special Phare committee. Finance Memorandum, which is a base of financing, was signed on 11 December 2000.

The Phare 2001 programme is fully intended for investments, namely: in information and telecommunication equipment amounting to 2,15 million EUR, in technical equipment for the state border control amounting to 1,3 million EUR, in the establishment of Asylum home amounting to 1,55 million EUR and Aliens home amounting to 1 million EUR; the total amount being 6,0 million EUR. All these projects apart from the establishment of Aliens home and Asylum home represent the continuation of the projects of modernisation and equipping of Slovenian police, which were begun in previous years.

The resources from the Phare 99 budget and programme will ensure in the next few years a greater level of automatic data operation (e.g. optical reading of passports), the possibility of a faster transfer of more demanding data (fingerprints, photos) from border crossings to the central computer, better equipment of border crossings with a special technical control equipment and a greater number of units for state border control with the equipment for observation also in case of poor visibility.

Slovenia plans to achieve the state of full equipment which will allow the possibilities of implementation of police tasks at the future external EU border in line with "Schengen" standards by the end of 2003 with the resources from Phare 2000 programme and from the national budget, and with the information support of units responsible for the control of the future external border. A part of resources is intended for a special technical equipment of police to implement the tasks of state border control, and another part for the equipment for criminal investigation especially due to the needs to discover more demanding criminal offences related to the crossing of state border, which have become more and more organised and more difficult to prove in the last few years.

With the help of resources from Phare 2001 programme and funding from the national budget, Slovenia foresees further introduction of digital radio system (replacement of the outdated analogue radio system) in the area of green and blue borders, the introduction of an appropriate "back up" solution for the central computer which will ensure the best possible availability of SIS data, additional technical equipment to discover criminal offences related to state border crossing, and the observation of state border (also on the sea) in less favourable circumstances, especially at night. A gradual purchase of equipment funded both from Phare resources and from the national budget, is to bring Slovenia in the next few years to the level of technical equipping as it was presented in the results of the twinning project on state border control, terminated in August 2000.

In the years from 1997, when Slovenia first entered the PHARE programme, to the end of 2001, the total amount of granted resources is 16.674.372 million EUR. Of these, 1.550.000 EUR were spent for institution building and the rest  (15.124.372 million EUR) for the equipment of police and establishment of asylum home and Aliens home. Besides taking part in the National Phare programme, the ministry took part also in Phare multinational horizontal programmes, namely:

- Enfopol 118 – the programme was led by the AEPC - Association of European Police Colleges, 10 European Union Member States and 10 Joint Members took part in it. It consisted of 15 modules, five general ones (police ethics, police co-operation in Europe etc.) and 10 special ones (migration supervision, illicit drug trade, financial crime and money laundering etc.). The programme was begun in March 1999 and terminated in early 2001. Participating in the programme were approximately 70 employees of the Ministry of the Interior. Most programmes included also the representatives of other institutions (Ombudsman Office, Customs Administration, Government office of Drugs).

- Horizontal multinational Phare programme in the area of migration and asylum – the operative leaders of the programme were the German Federal Refugees Office (BAFl) and UNHCR. The programme consisted of six workshops, two round tables, two study visits and the visit of »evaluation« mission in Slovenia. The programme was begun in February 1999 and terminated at the end of 2000. Participating in the programme were 20 employees of the Ministry of the Interior and the representatives of other relevant institutions from the area of asylum and migration (Administrative Court, NGOs).

- The Ministry of Justice and the ministry of the Interior will participate in the new Phare Horizontal programme too. The justice cooperation foresees the participation in three projects (modules): in the area of rule of law, judicial cooperation in penal matters, and training of judges in European Community Law. The Ministry of the Interior will participate in the following projects from the area of migration: state border control, visa policy and aliens issue.

In addition, the Ministry of the Interior makes use of technical assistance provided by the TAIEX (Technical Assistance Exchange Office) in the following tasks: preparation of the legislation in the area of explosives, establishing the level of compliance of our computer traffic accident databases with the EU requirements. Similar assistance was provided also in the area of weapon, and is planned in the area of crime (family violence, torture - planned in early 2001).

In November 1999, in the framework of bilateral cooperation, the Ministry of the Interior of the Republic of Slovenia and the Federal Ministry of the Interior of the Federal Republic of Germany signed an agreement on co-operation in equiping and training of police in the area of state border control and combat against transborder crime from 1999 to 2002. This agreement foresees a technical assistance for the implementation of state border control.

### 6.2 Financial Realisation Plan of the Project of Setting Up State Border Control on the Future External Border of the European Union

The Ministry of the Interior has, in line with the provisions of Accession Partnership, stood as a candidate with the projects for co-financing from PHARE resources in the framework of financial memoranda for years 1999, 2000, 2001 and 2002, these resources were taken into account besides budget resources in the financial construction framework. Hereby it needs to be stressed that the Financial memorandum of the Phare 2001 programme has not been signed and that a proposal was made for 2002, so the dynamics of exploiting resources by individual programmes depends also on their acceptance, realisation of public tenders, contracting and other circumstances.

Several elements have to be observed in the framework of financial plan for an integrate establishment of state border control. These are: costs for the purchase of special technical equipment for state border control, information-telecommunication equipment, material costs for newly employed police officers, costs for the provision of suitable working conditions, social conditions of the employees, expert education and training and other. Resources which need to be granted for the establishment of the future external EU border in the technical sense consist of costs for the purchase of special technical equipment for state border control, two helicopters and information-telecommunication equipment. Total costs of the planned technical equipment amount to about 10.000 billion SIT (45,947.724 EUR). The co-financing foreseen in the framework of PHARE Programme (investments) amounts to about 4.000 billion SIT (18,651.846 EUR).

Estimated necessary resources – financing sources (in EUR):

| Type of Equipment | Estimated Value | Financing Sources |  |  |
| --- | --- | --- | --- | --- |
|  |  | PHARE resources | Obligations of MF – co-financing | Regular budget |
| Special equipment for state border control | 15.969.100 | 9.532.359 | 5.933.600 | 503.241 |
| Helicopters | 9.260.000 | 0 | 1.525.000 | 7.735.000 |
| IT equipment | 20.718.624 | 9.119.487 | 10.681.417 | 917.720 |
| Total (EUR) | 45.947.724 | 18.651.846 | 18.139.917 | 9.155.961 |
| Total SIT (1 EUR = 216 SIT) | 9.924.708.278 | 4.028.798.758 | 3.918.222.022 | 1.977.687.498 |

Funding of Technical Equipment - annual presentation (in EUR):

| Type of equipment | Estimated value | Funding by year |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 | After 2005 |
| Special equipment | 15.969.100 | 58.500 | 1.773.295 | 2.375.000 | 3.674.372 | 4.211.550 | 3.876.383 | 0 |
| Helicopters | 9.260.000 | 0 | 255.000 | 1.000.000 | 1.725.000 | 1.800.000 | 1.800.000 | 2.680.000 |
| IT equipment | 20.718.624 | 2.104.020 | 4.358.662 | 2.222.773 | 3.833.169 | 4.400.000 | 3.800.000 | 0 |
| Total (EUR) | 45.947.724 | 2.162.520 | 6.386.957 | 5.597.773 | 9.232.541 | 10.411.550 | 9.476.383 | 2.680.000 |

Dynamics of Realisation of Purchase of Technical Equipment (annual presentation):

| Type of equipment | Estimated value | Dynamics of realisation |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 | Total |
| Special equipment | 15.969.100 | 0,37 % | 11 % | 15 % | 23 % | 26 % | 24 % | 100 % |
| Helicopters | 9.260.000 | 0 % | 0 % | 50 % | 50 % | 0 % | 0 % | 100 % |
| IT equipment | 20.718.624 | 10 % | 21 % | 11 % | 19 % | 21 % | 18 % | 100 % |
| Total (EUR) | 45.947.724 | 5 % | 14 % | 13 % | 24 % | 23 % | 21 % | 100 % |

Besides these costs, the integrate establishment of state border control will include the following: resources to purchase personal equipment for newly employed police staff; resources to ensure working conditions (newly constructed or adapted facilities) of the police, provide for social and housing needs of newly employed, education and training, payments for newly employed, and other.

7. INFRASTRUCTURE PROGRAMME FOR THE FUTURE EXTERNAL BORDER OF THE EUROPEAN UNION

7.1 Activities of the Government of the Republic of Slovenia for the setting up of the external border of the European Union (infrastructure)

The activities of the Government of the Republic of Slovenia in setting up the external border of the European Union and the state border between the Republic of Slovenia and the Republic of Croatia have been going on since 1998 when the Government defined border control points at the state border with the Republic of Croatia. Several measures were adopted during the last year alone; the following were among them:

- at the 5th meeting held on 29 June 2000, the Government authorised the Minister of the interior to coordinate the preparations for the establishment of the future external border of the EU on the border with the Republic of Croatia. The Ministry of the Interior was authorised to prepare the report of the completed tasks;

- at the 9th meeting, on 27 July 2000, it adopted the Report on Coordination of preparations to establish the safety, customs and inspection control at the future external border of the EU prepared by the working group from the Ministry of the Interior, and authorised ministers and heads of government services competent for finances, agriculture, forestry and food, health, economic relations and development, environment and spatial planning, transport and communications, external relations, area of informatics, European affairs and common services of the Government of the Republic of Slovenia to appoint the representatives to the Coordination (interministerial) committee and prepare the reports on the existing course of activities in establishing control of the future external border of the European Union;

- at the 15th meeting held on 7 September 2000, the Government of the Republic of Slovenia discussed the Information on the Course of Activities in Establishing Safety, Customs and Inspection Supervision at the future external border of the European Union;

- at the 20th meeting held on 12 October 2000, the Government of the Republic of Slovenia established the Coordinated (interministerial) committee to establish security, customs and inspection control;

- at the 4th meeting held on 21 December 2000, the Government of the Republic of Slovenia established the Ministerial coordination to establish security, customs and inspection control at the external border of the European Union (it replaced the interministerial committee) led by the minister competent for European affairs. Members are ministers competent for finance, internal affairs, agriculture, forestry and food, health, environment and spatial planning, transport and communications, external relations, and the Secretary General of the Government of the Republic of Slovenia. The committee sets directions and starting points for the preparation of projects, measures and activities to be implemented by individual task holders, co-ordinates and supervises activities of task holders, makes initiatives and proposes organisational, staff, financial and other measures concerning the establishment of safety, customs and inspection supervision at the future external border of the European Union;

- at the 10th meeting held on 1.2.2001, the Government of the Republic of Slovenia adopted the decisions on the responsibility of individual bodies/authorities in the implementation of the programme, which authorised the Ministry of the Environment and Spatial Planning for the preparation of the Decree of the location plan of a motorway section Krška vas – Obrežje as the basis of the preparation of implementation documentation, purchase of land and building of border crossing (Obrežje). Further, Joint Services of the Government of the Republic of Slovenia was appointed as an authorised investor for all programmes of investments and investment maintenance of border crossing in road, rail, air and maritime traffic - in the preparation of investment programmes its priorities are building and adaptation of border inspection posts (BIPs). Furthermore, the Joint Services of the Government took over the operation and day-to-day maintenance of all facilities and surfaces in border crossing area, which used to be a task of individual services implementing their tasks on border crossings.

7.2 Activities of bodies responsible for the setting up of security and customs controls and inspection control

The implementation of provisions of the acquis in the area of state border control requires several relatively independent areas of state bodies activity. From the aspect of functional competences, several »control« systems have to be established at the future external border with different functions of control: Schengen – security system; customs control; phyto-sanitary and other types of inspection and supervision.

The implementation of tasks in these areas has different dimensions. The work of inspection services is thus limited to just some border crossings, while the work of police and customs includes the control on all border crossings and, from the aspect of police competence, also the protection of the entire length of »green« and »blue« borders (as well as several accompanying measures in the area of the entire country). In terms of competences and obligations of individual national bodies connected with the state border control, and as regards functionality and purpose, three groups of border crossings have been distinguished:

- border crossings of key importance for personal transport, transport of goods, animals and food over the future external borders of the European Union,

- other international and interstate border crossings, and

- border crossings for border trade which still need to be built but are equally important for the tasks of police and customs control.

Competent for the tasks performed on border crossings and for the supervision of state border crossings are especially the Ministry of the Interior, The Ministry of Finance, the Ministry of Agriculture, Forestry and Food, and the Ministry of Health. In the framework of their obligations in establishing the future external border of the European Union they implemented a number of tasks both in legislative sense, or in the sense of the adoption of the acquis, and in the establishment of individual systems of technical protection or information – telecommunication systems and connections.

The Ministry of the Interior (Police) is responsible for the security supervision of state border crossing and for an integral implementation of Schengen acquis and standards. With the assistence of partner states (Germany, Austria) they defined in the framework of "Twinning" programmes the necessary assumptions for the establishment of the state border control, which are the following: technical standards of state border control, of border crossing control, necessary technical equipment for the establishment of information system, staffing structure, programmes of expert training to meet these standards and of training of trainers of training, and legal acts which the Republic of Slovenia has to adopt for the full implementation of the Schengen acquis. In this context, the projection of employment in the police for the 2000-2005 period was prepared in the employment area.

An integral programme of technical equipment purchase for the period until 2005 has been prepared too, specifically for the following purposes: implementation of police tasks in state border control (border control and border protection outside border crossings), special equipment for state border control (vehicles, vessels, helicopters), criminalist technical equipment for state border control, protection equipment, for special technical means and tools (termovision control system) and other.

Establishment and implementation of the custom control is the responsibility of the Ministry of Finance and the Customs Administration of the Republic of Slovenia. 30 customs offices are active on the border with the Republic of Croatia. In 1999, the equipment to combat smuggling and control illegal import on border crossings and the equipment of customs lab was purchased in the framework of the national Phare programme. Within the Phare 2000 programme the Customs Service will implement also the project which will allow the customs administration to meet the standards and requirements of the European Union and present the technical assistance in preparations on reorganisation of customs service at the accession to the European Union. Besides this, 2000 saw the continued cooperation in the area of Multi-Country Customs Programme and in programmes Mathaeus and Fiscalis in the areas of excise duty and VAT. 97% of all customs services are already implemented through the Customs Information System (CIS). In the future they plan to increase the number of transfer ways and communication connections, and to modernise the operation (electronic).

The implementation of inspection control is the responsibility of the Ministry of Agriculture, Forestry and Food (Veterinary administration of the RS and Inspectorate for Agriculture, Forestry, Hunting and Fisheries). For the needs of veterinary and phytosanitary inspection service, project documentation in line with the EU standards (equipment, facilities, staff) is being prepared for all three road »border inspection posts« (BIP).

Veterinary border crossings have been connected in a uniform network of information system of the Government of the Republic of Slovenia since 1 September 2000 and in special veterinary information system of the Veterinary Administration of the RS. Veterinary administration included veterinary border crossings in the ANIMO system and thus technically prepared the conditions for the transfer of decisions of fulfilling the conditions of veterinary consignments from the administration to the border crossing. For a complete harmonisation with the acquis the Republic of Slovenia will also adopt the Veterinary Act which the Government of the Republic of Slovenia already proposed to the National Assembly for discussion and which will replace the currently valid and non-harmonised Veterinary Service Act (OJ RS, No. 82/94, 21/95, 16/96 and 100/99). Both inspections are currently training inspectors for implementation of standards and procedures of the European Union concerning import. Procedures will be fully brought in line by September 2001 (phytosanitary inspection), and by the end of 2002 respectively (veterinary inspection).

The implementation of health inspection at the future external border of the EU will be carried out by the health inspection as well.  At the state border the Health Inspectorate controls mainly: import of non-animal origin food; objects and materials coming in contact with food; toys, cosmetics, tobacco and tobacco products, medicine and medical aids, dangerous chemicals, different sources of radiation. In special cases the control is also carried out to prevent  entry of contagious diseases. A special attention is given in particular to the control of products imported from third countries (Council Regulation of 8 February 1993 on checks on conformity with the rules on product safety in the case of product imported from third countries, 93/583/EEC; Commission Decision of 29 July 1993 establishing the list of products provided for in Article 8 of Council regulation No 339/93/). In the field of health control concerning food it is necessary to intensify  control on import of all kinds of food, which is evident from the provisions of the White Paper of the EU Commission (White Paper on food safety).

The Health Inspectorate of the Republic of Slovenia executes its control on 11 branch offices on the regional border units. On the future external border of the European Union control will be carried out on road border crossing points (Obrežje, Jelšane in Gruškovje), for maritime traffic at the port of Koper, for air traffic at the airport Ljubljana - Brnik, and for railway traffic at the railway station Dobova.

###### 7.3 The Plan to Establish »Border Inspection Points« and Build or Renovate Border Crossings at the State Border with the Republic of Croatia, and Control of Future External Border of the European Union

Land and river state border with the Republic of Croatia is 670 km long. It has 36 border crossings; 24 of these are international (8 rail crossings) and 12 are interstate border crossings. As the Agreement on Border Traffic and Cooperation with the Republic of Croatia has been implemented, the length of the border area will be about 20 km, with 27 border crossings for border traffic established to exercise the "Schengen" standard control.

All forms of border control (police, customs and inspection form) will be performed only at the defined »border inspection posts« (BIPs) which have been already determined by the conclusions of the Government of the Republic of Slovenia (adopted at 57th meeting held on 9 April 1998). At the road border crossings, these will be the following:

- Obrežje (combined veterinary crossing for animals and food),

- Jelšane  (border crossing for food),

- Gruškovje (border crossing for food).

Border crossing control will be performed also at the rail, air and maritime border crossings. The Government of the Republic of Slovenia (at the meeting held on 29 November 2000) defined the following »border inspection posts«:

- Dobova – rail border crossing,

- Airport Ljubljana – Brnik – air border crossing,

- Seaport Koper – maritime border crossing.

In the past the current state analysis on all »border inspection posts« was made as a priority task. The summary of the analysis is the following:

- Interstate border Crossing Obrežje – border crossing is located on the border with the Republic of Croatia on the Ljubljana – Zagreb motorway, while the construction of Obrežje belongs in the motorway section Krška vas – Obrežje and is planned according to the modifications and amendments to the National Motorway Construction Programme  (NPIA – A, OJ RS, No. 41/98) to be started in 1999 and completed in 2001. The Ministry of Transport made outline schemes for a motorway in the border crossing area, outline scheme projects for administration facilities, and projects for urban and industrial waste waters. The location of the waste water treatment plant is set and projects for its implementation are compiled. Furthermore, the location of the border crossing was harmonised with Brežice Municipality. Municipal Council adopted the changes to municipal plan. The Government of the Republic of Slovenia adopted  (on 19 April 2001) Decree on location plan for the motorway section Krška vas – Obrežje, which provides the basis for  purchaseing of land, which is a precondition for the preparation of the final project for construction. According to the plan the construction of BIP Obrežje, the most demanding and extensive project (area 224.000 m2), on the future external border will be finished in July 2002.

- Interstate border crossings Jelšane and Gruškovje – the area of either of these border crossings has not been fully defined or set. Working Group of the Republic of Slovenia for the Spatial Harmonisation with the Republic of Croatia has harmonised the microlocation of the Jelšane border crossing on the talks with the representatives of the neighbouring country. A proposal was adopted concerning the trace of the future new fast road or motorway from Jelšane past Ilirska Bistrica with the connection to the existing motorway between Postojna and Divača. A project task representing the preparation phase for the compilation of project documentation is being prepared.

- The microlocation of the Gruškovje border crossing facilities has not been set yet. The representatives of both countries advocated the consideration of possibility to establish a common border crossing as known in other EU Member States (common border crossing Nikelsdorff at the state border between Austria and Hungary).

- Rail border crossing Dobova, air border crossing Ljubljana - Brnik, maritime seaport crossing Koper - for all three a renovation of facilities is planned; in Seaport Koper and at the Ljubljana airport in the framework of the existing border crossing surface, while for the rail crossing Dobova several possibilities are foreseen, among them also the establishment of a common border crossing with the Republic of Croatia.

In February 2001, Joint Services of the Government of the Republic of Slovenia made a summary and an evaluation of the state of affairs with proposed solutions also for each individual border crossing with the Republic of Croatia, which serves as a basis for the preparation of programme for the establishment of border crossings at the future external border of the European Union. The basis for the preparation of the programme is the analysis of the state and conditions at the existing border crossings. The programme of the establishment of border crossings is based on the data on spatial arrangement plans, traffic connections, transport frequencies, number of employees, location conditions for projecting, and meaningfulness of re-categorisation.

Joint Services of the Government as an authorised investor for border crossings, divided all border crossings on the border with the Republic of Croatia in three groups according to the priority order of construction or renovation:

- border crossings which will become border inspection posts (BIPs). This group includes: road border crossings - Obrežje, Gruškovje, Jelšane; rail crossing Dobova; Seaport Koper, airport Ljubljana – Brnik;

- border crossings with the planned public tenders for investment engineering and completed project tasks as a pre-preparation phases for the preparation of project documentation. These road border crossings are: Sečovlje, Sočerga, Podgorje, Starod, Metlika, Slovenska vas, Rigonce, Rogatec, Meje, Zavrč, Središče ob Dravi;

- border crossings for which the analyses of the state of affairs have been made: Dragonja, Babno Polje, Podplanina, Petrina, Vinica, Orešje, Bistrica ob Sotli, Imeno, Dobovec, Zgornji Leskovec, Ormož, Razkrižje, Gibina, Petišovci.

The current state are presented for all border crossings included in the project. Border crossing projects are conceived as completed functional units consisting of border crossing areas and named after the place where a border crossing is situated.

| ## Border Crossing |  | ### Categorisation |  | Works to be Completed by |
| --- | --- | --- | --- | --- |
| # OBREŽJE |  | Interstate border crossing for passenger and goods transport BIP, HC |  | June 2002 |
| GRUŠKOVJE |  | Interstate border crossing for passenger and goods transport BIP, HC |  | January 2003 |
| JELŠANE |  | Interstate border crossing for passenger and goods transport BIP, HC |  | January 2003 |
| # ŽP DOBOVA |  | Interstate border crossing for passenger and goods transport BIP |  | January 2003 |
| # BRNIK AIRPORT |  | Interstate border crossing for passenger and goods transport BIP |  | January 2003 |
| # KOPER PORT |  | Interstate border crossing for passenger and goods transport BIP |  | January 2003 |
| # SEČOVLJE |  | Interstate border crossing for passenger and goods transport |  | September 2002 |
| # SOČERGA |  | Interstate border crossing for passenger and goods transport |  | September 2002 |
| # PODGORJE | Interstate border crossing for passenger and goods transport |  | September 2002 |  |
| # STAROD | Interstate border crossing for passenger and goods transport ZN |  | September 2002 |  |
| METLIKA | Interstate border crossing for passenger and goods transport |  | September 2002 |  |
| SLOVENSKA VAS | Interstate border crossing for passenger transport |  | September 2002 |  |
| RIGONCE | Interstate border crossing for passenger and goods transport |  | September 2002 |  |
| # ROGATEC | Interstate border crossing for passenger transport |  | September 2002 |  |
| MEJE | Interstate border crossing for passenger transport |  | September 2002 |  |
| ZAVRČ | Interstate border crossing for passenger and goods transport |  | September 2002 |  |
| SREDIŠČE OB DRAVI | Interstate border crossing for passenger and goods transport |  | September 2002 |  |
| DRAGONJA | Interstate border crossing for passenger and goods transport |  | January 2003 |  |
| BABNO POLJE | Interstate border crossing for passenger and goods transport |  | January 2003 |  |
| # PODPLANINA | Interstate border crossing for passenger transport |  | June 2002 |  |
| # PETRINA | Interstate border crossing for passenger and goods transport |  | January 2003 |  |
| VINICA | Interstate border crossing for passenger transport |  | January 2003 |  |
| OREŠJE | Interstate border crossing for passenger transport |  | June 2002 |  |
| BISTRICA OB SOTLI | Interstate border crossing for passenger and goods transport |  | June 2002 |  |
| # IMENO | Interstate border crossing for passenger and goods transport |  | January 2003 |  |
| # DOBOVEC | Interstate border crossing for passenger and goods transport |  | January 2003 |  |
| ZGORNJI LESKOVEC | Interstate border crossing for passenger transport |  | June 2002 |  |
| ORMOŽ | Interstate border crossing for passenger transport |  | January 2003 |  |
| RAZKRIŽJE | Interstate border crossing for passenger transport |  | June 2002 |  |
| GIBINA | Interstate border crossing for passenger and goods transport |  | June 2002 |  |
| PETIŠOVCI | Interstate border crossing for passenger and goods transport |  | January 2003 |  |

The plan and the priority order of construction of border crossings are made on the basis of development importance of projects, transport connections, project preparation stages and the present state of affairs. The table defines priority projects in border crossing construction according to these indicators.

| # Border Crossing | Development Imortance | Transport Connection | Phase Realisation of Project | Spatial Arrangement Plan | Land Registry State | Priority |
| --- | --- | --- | --- | --- | --- | --- |
| # OBREŽJE | *** | ** | * | * | * | 1 |
| GRUŠKOVJE | *** | * |  |  |  | 1 |
| # JELŠANE | *** | * |  |  |  | 1 |
| # ŽP DOBOVA | *** | *** | * | * | * | 1 |
| # LETALIŠČE # BRNIK | *** | *** | * | * | *** | 1 |
| # LUKA # KOPER | *** | ** | * | * | *** | 1 |
| # SEČOVLJE | ** | *** | * | * | ** | 2 |
| # SOČERGA | ** | ** | * | * | * | 2 |
| # PODGORJE | ** | ** |  |  |  | 2 |
| # STAROD | *** | ** | * | * | * | 2 |
| METLIKA | ** | *** | * | * | * | 2 |
| SLOVENSKA VAS | ** | *** | * |  | ** | 2 |
| RIGONCE | ** | *** | * | * | * | 2 |
| # ROGATEC | ** | *** | * | ** | * | 2 |
| MEJE | ** | *** | * | * | * | 2 |
| ZAVRČ | ** | *** | * | * | * | 2 |
| # SREDIŠČE # OB DRAVI | ** | *** | * |  | * | 2 |
| DRAGONJA | ** | * |  |  |  | 2 |
| BABNO POLJE | ** | *** | * | * |  | 2 |
| # PODPLANINA | * | * | * | * | * | 3 |
| # PETRINA | ** | *** | * |  | * | 2 |
| VINICA | ** | ** | * | * | * | 2 |
| OREŠJE | ** | *** | * | * | * | 2 |
| BISTRICA OB SOTLI | ** | *** | * |  | * | 2 |
| IMENO | * | * | * |  | * | 2 |
| # DOBOVEC | ** | ** | * | * |  | 2 |
| ZGORNJI LESKOVEC | * | ** | * | * | * | 3 |
| ORMOŽ | ** | * | * | * | * | 2 |
| RAZKRIŽJE | * | *** | * |  | * | 3 |
| GIBINA | ** | *** | * |  | * | 2 |
| PETIŠOVCI | ** | * | * | * | ** | 2 |

The state border control tasks of the police include border controls, control of movement at border crossing points and tasks relating to: the determination and designation of border crossing point areas and border control areas; the carrying of weapons and ammunition across the state border; the construction of facilities at border crossing points; the protection of the state border between border crossing points; checking the suitability of border markings; the construction of facilities in an area up to 50 metres from the border line; identifying and dealing with border incidents and other violations of the inviolability of the state border; control of crossing the state border between official border crossing points on the basis of special permits.

A border police station with a specialised area of operation is a police unit whose officers carry out border control and other police tasks exclusively at border crossing points. A border police station with a combined area of operation is a police unit whose officers carry out border control at border crossing points, protection and other police tasks on the state border between official border crossing points and all general police tasks within the station's territory. The majority of tasks carried out by the officers of such units relate to border issues. A police station with a combined area of operation is a police unit whose officers carry out all general police tasks within the station's territory, border control and other police tasks at border crossing points and protection and other police tasks on the state border between official crossing points in the station's territory. The majority of tasks carried out by the officers of such units are general police tasks.

- Key: *** - the highest priority rank, transport connections, spatial arrangement plan, land registry state; ** - medium indicator rank; * - lowest indicator rank (initial phase of a project).